## Monday 9.21.26
Email daily to: Rav Sandhu, Sherree Martin, Ron Scott, Adrian Silva, Yvonne Rodriguez, Kofi Oduro, Melissa Gardynik; Scott Jones Email report daily at 5 pm.
EAP Daily Update - Monday 9.21.26 - Submitted to Executive Team by 5 pm
Responsible Party | Measurable | Status G/Y/R | Comments / Explanation
Nicole | EHS | G
Nicole | Staffing Issues | G | 2026 Q3 DL Requirement: 41 Staffing Changes: New Hire: Total EAP Employees minus LOA DL: 35 (1st 24 - 2nd 10) IDL: 25 (1st 18 - 2nd 7) Total Present: DL = 1st - 20.5, 2nd - 9 IDL = 24 Planned Absenteeism: DL: 1st shift: Sophy Sou, Char Z., Zaki Iskandaron, James Farmer - EO @ 12:30p IDL: 1st shift: DL: 2nd Shift: IDL: 2nd Shift: Unplanned Absenteeism (call off/leave early): DL 1st shift - Debbie Heacock IDL 1st Shift - DL 2nd Shift - Savon Newberry IDL 2nd Shift: John Stanley Other: LOA -DL -Jerry Weick (ERTW September - December), Merritt Higgins (TBD), HaiCi Huang (9/15-10/16)
| Current Year Program EOP | G | Guelph RDX - April 2026 GM A2SL (CT4) - June 2026 GM 610 (extended cargo van-U-Haul - Springfield) - September 2026
Michelle | Prem. Freight / Customer Notes | G | No premium freight.
Michelle | On Time Delivery | G | Voestalpine: 307/308 dust shields: Will run following audit in PA118. Voestalpine has 2 weeks of coverage.
Michelle | Customer Invty Status Red = 1 day on hand Yellow = 2 days on hand Green = 3 days on hand |  | Customer | Program# | # of parts supplied
|  | G | Adient - Clanton | TYAA | 8 | Inventory coverage until 9/28 5300920/5301824 running in PA118
|  | G | Adient - Lakewood | TYAA | 20 | Inventory coverage until 10/1
|  | Y |  | TYAA | 4 | Inventory coverage until 9/23 32495 next in PA116, tooling working on red tag for bad form.
|  | G | GM - BWLGRN | TYAA | 8 | Inventory coverage until 10/1
|  | G |  | C1UL | 15 | Inventory coverage until 9/28
|  | G |  | Y1XX | 1 | Inventory coverage until 2/8
|  | G | GM-Factory Zero | BT1TL | 7 | Inventory coverage until 9/30
|  | G | GM-Wentzville | D2UC | 1 | Inventory coverage until 10/14
|  | G |  | GMT610 | 2 | Extended size cargo van (used for U-Haul) building out this week. No further requirements.
|  | Y |  | GMT610 | 8 | Inventory coverage until 9/23 5278 running in PA117 and W303.
|  | G | GAP | WS | 2 | Inventory coverage until 9/28 17511's at Detroit Coatings.
|  | Y | OP M (HBPO) | RU | 3 | Inventory coverage until 9/23 USF shipments will be Wed/Fri this week.
|  | G | Metalsa | UX71 | 2 | Inventory coverage until 10/5
|  | G | SLP | KM EJ | 5 | Inventory coverage until 11/16
|  | G | Stellantis | LB | 2 | Inventory coverage until 10/13
|  | G | Toyo-Imlay City | 500B | 10 | Inventory coverage until 10/2
|  | G | Toyo-Tennesee | L42P | 2 | Inventory coverage until 10/2
|  | R | Voestalpine | G01 | 4 | Inventory coverage until 9/21. 307/308 job 3 in PA118, will follow audit.
|  | G | Voestalpine | BR167 | 18 | Inventory coverage until 9/24
Michele | SERVICE | G | ~84141998 and 85609492 complete for this week's CCA truck. ~23429897/23429898: GM Argentina order, waiting on commercial resolution. Hopefully by end of September. ~12608820: Steel received. Running in PA115 today, then heat treat and zinc. ~22799575: Pending direction/review of 1804 from GM CCA team. ~23445040: Pending direction/review of 1804 from GM CCA team. ~22717995: Pending direction/review of 1804 from GM CCA team.
Jeff Potter | Supplier Issues | G | No issues.
John W | Labor / Overtime | G | None
John W. | Daily Efficiency 85%> = Green 69-84% = Yellow 69% < = Red |  | Work Center Group | % | Notes
96%
89%
86%
N/A
John W | Downtime Analysis |  |  | TTL Hours | Reason Percentage | Notes
|  |  | Daily DT | 15.47
PA119: Low air pressure. WC39: Bad shunt cable.
PA116: Die protection wire. PA117: Galling.
1st shift 9/21: PA110: Set C46892 (1.07hrs) PA115: Set C08820 (1.00hrs) PA117: Set 95278-20 (1.5hrs)
John W | Operations Update - Critical Issues | G | 2nd shift 9/18: Plant closed 1st shift 9/21: PA119 - Low air pressure x4. (41mins DT) PA118 - Steel buckled. (22mins DT) PA116 - Replaced wire for die protection (25mins DT) PA4 - Pilot stuck open. (12mins DT) PA117 - Galling. (45mins DT) WC39 - Bad weld, large nut breaking off. Maintenance found a bad shunt cable. (2.65hrs DT)
John W | MFG Mishit Reports | G | None
John W | Housekeeping | G | Cleaned bathrooms Cleaned lunch area Dumped trash Worked on floors. Replaced old/missing red totes at work centers.
John W | Change Overs
Scott | TOOLING | G | 9/21 1ST SHIFT: C79305/405: 100% - TRIM CHANGE. 7.42 HOURS C80600/700: 10% - OP PANEL STICKING. .82 HOURS C93624/5: 100% - FLAT FLANGE/DEAD NITRO. 6.9 HOURS C17510/511: 50% - FPM. 1.2 HOURS 2332495: 60% - BAD FORM. 4.58 HOURS. C42582/71159: 100% - PULLING SLUGS. 4.58 HOURS PRESS CALLS: PA117: 95278-20 - GALLING. .2 HOURS. MERLIN POLISHED RADIUS ON LOWER DRAW. EXPLAINED TO OPERATOR THAT LOWER NEEDS THE DRAW LUBE NOT THE UPPER. SCHEDULED/UNSCHEDULED: GREG WEICK: 8.24/0 = 8.24 HOURS MERLIN TACKETT: 8.1/.2 = 8.3 HOURS JEFF ROSE: 8.25/0 = 8.25 HOURS TOOLING DOWNTIME: .2 HOURS WORKCENTER LOGS: .81 HOURS
Diego | Maintenance | G | PW-39: Cold Welds, Found damaged Shunt cable. Parts on order. PA50: Pulled Covers to inspect clutch. PA114: Worked on getting the press powered up.
Yvonne | Quality Concerns |  | PA120 ¦ 724151H10B ¦ No new issues PA119 ¦ 724794H05C ¦ No new issues PA118 ¦ C93624 ¦ No new issues PA117 ¦ ¦ No new issues PA116 ¦ ¦ No new issues PA115 ¦ ¦ No new issues PA112 ¦ ¦ No new issues PA111 ¦ ¦ No new issues PA110 ¦ ¦ No new issues PA50 ¦ ¦ No new issues SSL ¦ 20007/8-AC ¦ No new issues Welding ¦ ¦ Customer ¦ ¦ No new issues Supplier ¦ ¦ No new issues Internal ¦ ¦ GM CCA - Shipments ¦ ¦ No issues to report

## Tuesday 9.22.26
Email daily to: Rav Sandhu, Sherree Martin, Ron Scott, Adrian Silva, Yvonne Rodriguez, Kofi Oduro, Melissa Gardynik; Scott Jones Email report daily at 5 pm.
EAP Daily Update - Tuesday 9.22.26 - Submitted to Executive Team by 5 pm
Responsible Party | Measurable | Status G/Y/R | Comments / Explanation
Nicole | EHS | G
Nicole | Staffing Issues | G | 2026 Q3 DL Requirement: 41 Staffing Changes: Termed Malachi Thomas (2nd shift) New Hire: Total EAP Employees minus LOA DL: 35 (1st 24 - 2nd 9) IDL: 25 (1st 18 - 2nd 7) Total Present: DL = 1st - 22, 2nd - 8 IDL = 24 Planned Absenteeism: DL: 1st shift: Pam Bryson, Sophy Sou IDL: 1st shift: DL: 2nd Shift: IDL: 2nd Shift: Unplanned Absenteeism (call off/leave early): DL 1st shift - IDL 1st Shift - DL 2nd Shift - Savon Newberry IDL 2nd Shift: John Stanley Other: LOA -DL -Jerry Weick (ERTW September - December), Merritt Higgins (TBD), HaiCi Huang (9/15-10/16)
| Current Year Program EOP | G | Guelph RDX - April 2026 GM A2SL (CT4) - June 2026 GM 610 (extended cargo van-U-Haul - Springfield) - September 2026
Michelle | Prem. Freight / Customer Notes | G | No premium freight.
Michelle | On Time Delivery | G | Voestalpine: 307/308 dust shields: Will run following audit in PA118. Voestalpine has 2 weeks of coverage.
Michelle | Customer Invty Status Red = 1 day on hand Yellow = 2 days on hand Green = 3 days on hand |  | Customer | Program# | # of parts supplied
|  | G | Adient - Clanton | TYAA | 8 | Inventory coverage until 10/2
|  | G | Adient - Lakewood | TYAA | 20 | Inventory coverage until 10/1
|  | R |  | TYAA | 4 | Inventory coverage until 9/23 32495 red tag completed at 2pm today. Running in PA116 as of 4pm.
|  | G | GM - BWLGRN | TYAA | 8 | Inventory coverage until 10/1
|  | G |  | C1UL | 15 | Inventory coverage until 9/28
|  | G |  | Y1XX | 1 | Inventory coverage until 2/8
|  | G | GM-Factory Zero | BT1TL | 7 | Inventory coverage until 9/30
|  | G | GM-Wentzville | D2UC | 1 | Inventory coverage until 10/14
|  | G |  | GMT610 | 2 | Extended size cargo van (used for U-Haul) building out this week. No further requirements.
|  | R |  | GMT610 | 8 | Inventory coverage until 9/23 5278 running in PA117 and W303. Sent parts to Midwest today, they will be ready for pickup at 10am tomorrow.
|  | G | GAP | WS | 2 | Inventory coverage until 9/28 17511's at Detroit Coatings.
|  | Y | OP M (HBPO) | RU | 3 | Inventory coverage until 9/24 USF shipments will be Wed/Fri this week.
|  | G | Metalsa | UX71 | 2 | Inventory coverage until 10/5
|  | G | SLP | KM EJ | 5 | Inventory coverage until 11/16
|  | G | Stellantis | LB | 2 | Inventory coverage until 10/13
|  | G | Toyo-Imlay City | 500B | 10 | Inventory coverage until 10/2
|  | G | Toyo-Tennesee | L42P | 2 | Inventory coverage until 10/2
|  | R | Voestalpine | G01 | 4 | Inventory coverage until 9/21. 307/308 next in PA118, will follow audit.
|  | G | Voestalpine | BR167 | 18 | Inventory coverage until 9/24
Michele | SERVICE | G | ~84141998 and 85609492 complete for this week's CCA truck. ~23429897/23429898: GM Argentina order, waiting on commercial resolution. Hopefully by end of September. ~12608820: Steel received. Running in PA115 today, then heat treat and zinc. ~22799575: Pending direction/review of 1804 from GM CCA team. ~23445040: Pending direction/review of 1804 from GM CCA team. ~22717995: Pending direction/review of 1804 from GM CCA team.
Jeff Potter | Supplier Issues | G | No issues.
John W | Labor / Overtime | G | None
John W. | Daily Efficiency 85%> = Green 69-84% = Yellow 69% < = Red |  | Work Center Group | % | Notes
54%
87%
92%
100%
John W | Downtime Analysis |  |  | TTL Hours | Reason Percentage | Notes
|  |  | Daily DT | 15.47
PA119: Low air pressure. PA118: Waiting on bolster to pump.
PA120: Oversized window, feeler fail. PA119: Hole off location. PA116: Bad form. PA110: Bad form.
1st shift 9/22: PA115: Set C41997 (.85hr) PA120: Set T5U2BF328/332C (1.23hrs) PA119: Set C20007/8 (1.48hrs) PA116: Set 2332495 (.87hr) PA118: Set C93624/93625 (2.3hrs) PA4: Set 3871159/3942582 (.95hr)
John W | Operations Update - Critical Issues | Y | 2nd shift 9/21: PA120: Scrap jam op30 and op10, lube fault. Lamination on beginning of coil. (40mins DT) PA119: Air pressure fault. Lower cam stuck, out of nitro. (1hr DT) PA118: Finger and sensor adjustments. (50mins DT) PA116: Added oil to gibs. (15mins DT). 1st shift 9/22: PA120: Oversized window on Toyo/Feeler fail (5.46hr DT) PA119: Low air pressure. Cam issue. Hole off location (2.98hr DT) PA118: Steel issue, too wide for entry guiderail. Could be caused by straightener. Waiting on bolster to pump up (3hr DT) PA116: Bad form after C/O (.25hr DT) PA110: Bad form (.5hr DT) PA4: Pilot release stuck open (.25hr DT)
John W | MFG Mishit Reports | G | None
John W | Housekeeping | G | Cleaned bathrooms Cleaned lunch area Dumped trash Cleaned floors.
John W | Change Overs
Scott | TOOLING | Y | 9/21 2ND SHIFT: 724150H11B: 100% - TRIM AND HOLE BURRS. 4.32 HOURS C15013/15207: 30% - TRIM AND HOLE BURRS. 6.02 HOURS OPENING ADIENT DIES FOR PICS. 9.03 HOURS. 2332495: 80% - BURRS/BAD FORM. 9.41 HOURS. PRESS CALLS: PA119: C20002001 - CAM STUCK. .47 HOURS. ZACH PULLED CAM 1ST SHIFT TO FINISH. SCHEDULED/UNSCHEDULED: JESSE DENNIS: 10.34/0 = 10.34 HOURS JOHN GREEN: 9.03/0 = 9.03 HOURS. (CAME IN LATE) ZACH BRAMIGK: 10.03/0 = 10.03 HOURS TOOLING DOWNTIME: .47 HOURS WORKCENTER LOGS: 1.15 HOURS 9/22 1ST SHIFT: C80600/700: 50% - OP PANEL STICKING. 4.5 HOURS C17510/511: 60% - FPM. 8.09 HOURS 2332495: 100% - BAD FORM. 3.67 HOURS. PRESS CALLS: PA110: C46892 - BAD FORM. .37 HOURS. MERLIN LOWERED RAM. PA119: C20002001 - CAM HOLE BURRS. 2.42 HOURS. DECIDED TO PULL. PA120: C52328/32 - FEELER FAIL. 6.22 HOURS. JEFF ADJUSTED UPPER FORM PUNCH SEVERAL TIMES. WAS ABLE TO GET AN ACCEPTABLE PART. SCHEDULED/UNSCHEDULED: GREG WEICK: 5.92/2.42 = 8.34 HOURS MERLIN TACKETT: 8.09/.37 = 8.46 HOURS JEFF ROSE: 2.25/6.22 = 8.47 HOURS TOOLING DOWNTIME: 9.01 HOURS WORKCENTER LOGS: 8.32 HOURS
Diego | Maintenance | G | PA 114: Worked on Ross Valve issue, found bad contact. Replaced. Superb Working on the clutch and leveling the ram. Ram adjust is blowing fuses: Found bad overload protection. Replaced with different style overload, now power drops out as soon as you try to adjust the ram: Found limit switch is faulty. bypassed to let superb set up the ram. They will be back out tomorrow to adjust the ram and set the gibs. PA50: Removed the clutch plate to inspect the friction disc. Friction disc look good, We are now pulling the main gear cover to inspect the gear and intermediate drive. PA 118: Pilot roll regulator not working. Took apart and cleaned out.
Yvonne | Quality Concerns |  | PA120 ¦ 724151H10B ¦ No new issues PA119 ¦ 724794H05C ¦ No new issues PA118 ¦ C93624 ¦ No new issues PA117 ¦ ¦ No new issues PA116 ¦ ¦ No new issues PA115 ¦ ¦ No new issues PA112 ¦ ¦ No new issues PA111 ¦ ¦ No new issues PA110 ¦ ¦ No new issues PA50 ¦ ¦ No new issues SSL ¦ 20007/8-AC ¦ No new issues Welding ¦ ¦ Customer ¦ ¦ No new issues Supplier ¦ ¦ No new issues Internal ¦ ¦ GM CCA - Shipments ¦ ¦ No issues to report

## Wednesday 9.23.26
Email daily to: Rav Sandhu, Sherree Martin, Ron Scott, Adrian Silva, Yvonne Rodriguez, Kofi Oduro, Melissa Gardynik; Scott Jones Email report daily at 5 pm.
EAP Daily Update - Wednesday 9.23.26 - Submitted to Executive Team by 5 pm
Responsible Party | Measurable | Status G/Y/R | Comments / Explanation
Nicole | EHS | G
Nicole | Staffing Issues | G | 2026 Q3 DL Requirement: 41 Staffing Changes: New Hire: Total EAP Employees minus LOA DL: 35 (1st 24 - 2nd 9) IDL: 25 (1st 18 - 2nd 7) Total Present: DL = 1st - 21, 2nd - 8 IDL = 25 Planned Absenteeism: DL: 1st shift: Pam Bryson, Sophy Sou IDL: 1st shift: DL: 2nd Shift: IDL: 2nd Shift: Unplanned Absenteeism (call off/leave early): DL 1st shift - James Pulley IDL 1st Shift - DL 2nd Shift - Betty Halcomb IDL 2nd Shift: Other: LOA -DL -Jerry Weick (ERTW September - December), Merritt Higgins (TBD), HaiCi Huang (9/15-10/16)
| Current Year Program EOP | G | Guelph RDX - April 2026 GM A2SL (CT4) - June 2026 GM 610 (extended cargo van-U-Haul - Springfield) - September 2026
Michelle | Prem. Freight / Customer Notes | G | No premium freight.
Michelle | On Time Delivery | G | Voestalpine: 307/308 dust shields: In setup at PA118 4pm
Michelle | Customer Invty Status Red = 1 day on hand Yellow = 2 days on hand Green = 3 days on hand |  | Customer | Program# | # of parts supplied
|  | G | Adient - Clanton | TYAA | 8 | Inventory coverage until 10/2
|  | G | Adient - Lakewood | TYAA | 20 | Inventory coverage until 10/1
|  | Y |  | TYAA | 4 | Inventory coverage until 9/25 32495 running in PA116
|  | G | GM - BWLGRN | TYAA | 8 | Inventory coverage until 10/1
|  | G |  | C1UL | 15 | Inventory coverage until 9/28
|  | G |  | Y1XX | 1 | Inventory coverage until 2/8
|  | G | GM-Factory Zero | BT1TL | 7 | Inventory coverage until 9/30
|  | G | GM-Wentzville | D2UC | 1 | Inventory coverage until 10/14
|  | G |  | GMT610 | 2 | Extended size cargo van (used for U-Haul) building out this week. No further requirements.
|  | G |  | GMT610 | 8 | Inventory coverage until 9/28
|  | G | GAP | WS | 2 | Inventory coverage until 9/28 17511's at Detroit Coatings.
|  | Y | OP M (HBPO) | RU | 3 | Inventory coverage until 9/24 USF shipments will be Wed/Fri this week.
|  | G | Metalsa | UX71 | 2 | Inventory coverage until 10/5
|  | G | SLP | KM EJ | 5 | Inventory coverage until 11/16
|  | G | Stellantis | LB | 2 | Inventory coverage until 10/13
|  | G | Toyo-Imlay City | 500B | 10 | Inventory coverage until 10/2
|  | G | Toyo-Tennesee | L42P | 2 | Inventory coverage until 10/2
|  | R | Voestalpine | G01 | 4 | Inventory coverage until 9/23. 307/308 in setup at PA118.
|  | G | Voestalpine | BR167 | 18 | Inventory coverage until 9/25 151/153 next in PA120.
Michele | SERVICE | G | ~84141998 and 85609492 complete for this week's CCA truck. ~23429897/23429898: GM Argentina order, waiting on commercial resolution. Hopefully by end of September. ~12608820: Steel received. Running in PA115 today, then heat treat and zinc. ~22799575: Pending direction/review of 1804 from GM CCA team. ~23445040: Pending direction/review of 1804 from GM CCA team. ~22717995: Pending direction/review of 1804 from GM CCA team.
Jeff Potter | Supplier Issues | G | No issues.
John W | Labor / Overtime | G | None
John W. | Daily Efficiency 85%> = Green 69-84% = Yellow 69% < = Red |  | Work Center Group | % | Notes
75%
89%
98%
N/A
John W | Downtime Analysis |  |  | TTL Hours | Reason Percentage | Notes
|  |  | Daily DT | 15.47
PA119: Air pressure faults due to leaking counterbalance. PA116: rear light curtains not working. PS213: Nut feeder issues. PS66: Break monitor faults.
PA120: Hard mark. Oversized window. PA118: Bad form. Broken upper detail.
None
John W | Operations Update - Critical Issues | Y | 2nd shift 9/22: PA120: Hard mark on Toyo seat pans. Press stopping without fault x6. Feeler fail/bad form. (3.25hrs DT) PA119: Low air pressure faults from counterbalance leak. (1.5hrs DT) PA116: Feeler fail x2. (4hrs DT) 1st shift 9/23: PA120: Oversized window. Hard mark. (32mins DT) PA119: Low air pressure faults from counterbalance leak. Feeder short feeding. ((3.15hrs DT) PA118: Bad form. Upper form broke. Have to pull die. (10mins DT) PA116: rear light curtains not working (1.38hrs DT) PS213: Nut feeder not feeding correctly. (5mins DT) PS66: Break monitor faults (15mins DT)
John W | MFG Mishit Reports | G | None
John W | Housekeeping | G | Cleaned bathrooms Cleaned lunch area Dumped trash Cleaned floors.
John W | Change Overs
Scott | TOOLING | Y | 9/22 2ND SHIFT: C15013/15207: 50% - TRIM AND HOLE BURRS. 8.53 HOURS OPENING/CLOSING ADIENT DIES FOR PICS. 10.38 HOURS. C17510/511: 65% - FPM. 4.78 HOURS PRESS CALLS: PA116: 2332495 - BAD FORM. 4.88 HOURS. ZACH ADJUSTED FORM ANVILS. PA120: C52328/32 - BAD FORM. 1.58 HOURS. JESSE POLISHED FORM. SCHEDULED/UNSCHEDULED: JESSE DENNIS: 8.53/1.58 = 10.41 HOURS JOHN GREEN: 10.38/0 = 10.38 HOURS ZACH BRAMIGK: 5.28/4.88 = 10.16 HOURS TOOLING DOWNTIME: 6.46 HOURS WORKCENTER LOGS: 5.05 HOURS 9/22 1ST SHIFT: C80600/700: 80% - OP PANEL STICKING. 7.81 HOURS C17510/511: 80% - FPM. 8.45 HOURS 3693536: 20% - BURRS. 4.82 HOURS PRESS CALLS: PA120: C52328/32 - OVERSIZED RECTANGULAR OPENING. 2.54 HOURS. JEFF MADE SEVERAL ADJUSTMENTS THROUGHOUT THE DAY. WE HAVE A PLAN TO PERMANENTLY FIX. JUST NEED DIE OUT OF PRESS. TRYING TO GET IT THROUGH THIS RUN. PA118: C93624/5 - UPPER FORM BROKE. .07 HOURS. FOUND FRONT UPPER FORM BROKE. HAVE TO PULL DIE. SCHEDULED/UNSCHEDULED: GREG WEICK: 7.81/.62 = 8.43 HOURS MERLIN TACKETT: 8.45/.07 = 8.52 HOURS JEFF ROSE: 3.62/1.92 = 5.54 HOURS. (LEFT EARLY) TOOLING DOWNTIME: 2.61 HOURS WORKCENTER LOGS: 2.65 HOURS
Diego | Maintenance | G | PA 114: Main Motor will not start: Overloads blown. Superb worked on getting ram leveled. Press will cycle in inch but will not run in continuous. Getting a cycle stop from the PLC, still troubleshooting. PA50: 9/23/26: Got the flywheel cover removed, it did not give any clearance to see the Gear. We are putting the clutch back together to watch the press run with out the cover to see if we can identify any issues. in order to get to the main gear, the clutch and flywheel will need to be removed. Removed the clutch plate to inspect the friction disc. Friction disc look good, We are now pulling the main gear cover to inspect the gear and intermediate drive. PS-90: press stopping on the down stroke. Found prox sensor not being made on the crank shaft to let the press know it was in motion. PA 118: Feeder moving while running. The fasteners to the press were snapped off. Need to replace. PA 116: Press stopping: Re-aligned rear light curtains.
Yvonne | Quality Concerns |  | PA120 ¦ 724151H10B ¦ No new issues PA119 ¦ 724794H05C ¦ No new issues PA118 ¦ C93624 ¦ No new issues PA117 ¦ ¦ No new issues PA116 ¦ ¦ No new issues PA115 ¦ ¦ No new issues PA112 ¦ ¦ No new issues PA111 ¦ ¦ No new issues PA110 ¦ ¦ No new issues PA50 ¦ ¦ No new issues SSL ¦ 20007/8-AC ¦ No new issues Welding ¦ ¦ Customer ¦ ¦ No new issues Supplier ¦ ¦ No new issues Internal ¦ ¦ GM CCA - Shipments ¦ ¦ No issues to report

## Thursday 9.24.26
Email daily to: Rav Sandhu, Sherree Martin, Ron Scott, Adrian Silva, Yvonne Rodriguez, Kofi Oduro, Melissa Gardynik; Scott Jones Email report daily at 5 pm.
EAP Daily Update - Thursday 9.24.26 - Submitted to Executive Team by 5 pm
Responsible Party | Measurable | Status G/Y/R | Comments / Explanation
Nicole | EHS | G
Nicole | Staffing Issues | G | 2026 Q3 DL Requirement: 41 Staffing Changes: New Hire: Total EAP Employees minus LOA DL: 35 (1st 24 - 2nd 9) IDL: 25 (1st 18 - 2nd 7) Total Present: DL = 1st - 22, 2nd - 9 IDL = 24 Planned Absenteeism: DL: 1st shift: Pam Bryson, Sophy Sou IDL: 1st shift: DL: 2nd Shift: IDL: 2nd Shift: Unplanned Absenteeism (call off/leave early): DL 1st shift - IDL 1st Shift - DL 2nd Shift - IDL 2nd Shift: John Stanley Other: LOA -DL -Jerry Weick (ERTW September - December), Merritt Higgins (TBD), HaiCi Huang (9/15-10/16)
| Current Year Program EOP | G | Guelph RDX - April 2026 GM A2SL (CT4) - June 2026 GM 610 (extended cargo van-U-Haul - Springfield) - September 2026
Michelle | Prem. Freight / Customer Notes | G | No premium freight.
Michelle | On Time Delivery | G | Voestalpine: 307/308 dust shields: In setup at PA118, but press is down.
Michelle | Customer Invty Status Red = 1 day on hand Yellow = 2 days on hand Green = 3 days on hand |  | Customer | Program# | # of parts supplied
|  | G | Adient - Clanton | TYAA | 8 | Inventory coverage until 10/2
|  | G | Adient - Lakewood | TYAA | 20 | Inventory coverage until 10/1
|  | G |  | TYAA | 4 | Inventory coverage until 9/30
|  | G | GM - BWLGRN | TYAA | 8 | Inventory coverage until 10/1
|  | G |  | C1UL | 15 | Inventory coverage until 10/5
|  | G |  | Y1XX | 1 | Inventory coverage until 2/8
|  | G | GM-Factory Zero | BT1TL | 7 | Inventory coverage until 10/15
|  | G | GM-Wentzville | D2UC | 1 | Inventory coverage until 10/14
|  | G |  | GMT610 | 2 | Extended size cargo van (used for U-Haul) building out this week. No further requirements.
|  | G |  | GMT610 | 8 | Inventory coverage until 10/2
|  | G | GAP | WS | 2 | Inventory coverage until 9/28 17511's at Detroit Coatings.
|  | Y | OP M (HBPO) | RU | 3 | Inventory coverage until 9/25 USF shipments Wednesday and Friday this week.
|  | G | Metalsa | UX71 | 2 | Inventory coverage until 10/5
|  | G | SLP | KM EJ | 5 | Inventory coverage until 11/16
|  | G | Stellantis | LB | 2 | Inventory coverage until 10/13
|  | G | Toyo-Imlay City | 500B | 10 | Inventory coverage until 10/2
|  | G | Toyo-Tennesee | L42P | 2 | Inventory coverage until 10/2
|  | R | Voestalpine | G01 | 4 | Inventory coverage until 9/23. 307/308 waiting on PA118 to be released from maintenance.
|  | G | Voestalpine | BR167 | 18 | Inventory coverage until 9/28 151 running in PA120.
Michele | SERVICE | G | ~84141998 and 85609492 complete for this week's CCA truck. ~23429897/23429898: GM Argentina order, waiting on commercial resolution. Hopefully by end of September. ~12608820: Steel received. Running in PA115 today, then heat treat and zinc. ~22799575: Pending direction/review of 1804 from GM CCA team. ~23445040: Pending direction/review of 1804 from GM CCA team. ~22717995: Pending direction/review of 1804 from GM CCA team.
Jeff Potter | Supplier Issues | G | No issues.
John W | Labor / Overtime | G | None
John W. | Daily Efficiency 85%> = Green 69-84% = Yellow 69% < = Red |  | Work Center Group | % | Notes
54%
83%
85%
100%
John W | Downtime Analysis |  |  | TTL Hours | Reason Percentage | Notes
|  |  | Daily DT | 15.47
PA119: Feeder short feeding. PA118: Bolster issues, draining pit. PA50: Idle for maintenance. PS66: Break monitor faults. WC59: chiller faulted.
PA120: Shim stamp. Scrap in die. PA119: Undersize hole. Light part stamp. PA115: Spike burr. PA110: Strip sticking to rail.
2nd shift 9/23: PA120: Set 724153H07C PA119: Set 050372 1st shift 9/24: PA120: In-die C/O to 724151H12C PA118: Set 723307S00B/308 PA115: Set 4058424/4061731
John W | Operations Update - Critical Issues | R | 2nd shift 9/23: PA120: Lube fault x2. Oversized window. Ripples on seat pan. Bad air fitting swapped out. Ormac fault. (2.5hrs DT) PA119: Feeder short feeding. Low air pressure faults. (2.18hrs DT) PA118: Bolster won't pump up. (7hrs DT) PS214: Nut feeder jams, missing nuts (1.06hrs DT) 1st shift 9/24: PA120: Shimming PN stamp. Gripper adjustments. Scrap in the die. (1.6hrs DT) PA119: Undersized hole. Light part stamp. Feeder short feeding. (3.83hrs DT) PA118: Bolster wont pump. Issue with bolster clamp cylinders. Had to drain pit. (7hrs DT) PA116: Start of coil had rough edges (20mins DT) PA115: Spike burr (2.68hrs DT) PA110: Strip sticking to lower rail (11mins DT) PA50: Idle for maintenance. PS66: Maintenance working on break monitor system. Had to reset every 5-10 cycles. (15mins DT) WC59: Chiller faulted (1.01hrs DT)
John W | MFG Mishit Reports | G | None
John W | Housekeeping | G | Cleaned trash/kitchen/conference room in office from audit. Cleaned bathrooms Cleaned lunch area Dumped trash Worked on removing dead pine tree.
John W | Change Overs
Scott | TOOLING | Y | 9/23 2ND SHIFT: C15013/15207: 80% - TRIM AND HOLE BURRS. 8.77 HOURS OPENING/CLOSING ADIENT DIES FOR PICS. 10.47 HOURS. PRESS CALLS: PS213: 20007/8-20 - NO NUTS IN HEAD. .4 HOURS. NO TOOLROOM NEEDED WAS A MAINTENANCE ISSUE. NYLON TRACKS WERE DAMAGED. MIKE W REPAIRED. PA120: C52328/32 - RIPPLES/OVERSIZED HOLE. 1.1 HOURS. BO ADDED NITRO FOR RIPPLES. AND MADE ADJUSTEMENTS TO FORM PUNCH. SCHEDULED/UNSCHEDULED: JESSE DENNIS: 8.77/1.5 = 10.27 HOURS JOHN GREEN: 10.47/0 = 10.47 HOURS ZACH BRAMIGK: VAC DAY TOOLING DOWNTIME: 1.5 HOURS WORKCENTER LOGS: 1.61 HOURS 9/24 1ST SHIFT: C80600/700: 100% - OP PANEL STICKING. 3.37 HOURS. C17510/511: 90% - FPM. 5.3 HOURS. C30500/600: 100% - TRIM BURR. 2.2 HOURS 3693536: 90% - BURRS. 5.48 HOURS PRESS CALLS: PA119: 050372 - LIGHT STAMP/HOLE BURR. 2 HOURS. GREG REPLACED STAMP AND THEN SHIMMED RETAINER. ALSO SHARPENED PUNCH AND BUTTON. PA120: C15312 - LIGHT PART STAMP. .47 HOURS. MERLIN SHIMMED STAMP. PA115: C62476/64761 - SPIKE BURR. 2.48 HOURS. MERLIN SHARPENED UPPER/LOWER TRIM STEELS. PA110: C46892 - STRIP BUCKLING. .23 HOURS. MERLIN FOUND BAD SETUP. TOMMY CORRECTED. PA120: C15312 - SCRAP MARKS. .57 HOURS. JEFF FOUND TRIM STEEL IN BLANK HAD A SMALL CHIP. GROUND AWAY WITH HAND GRINDER. SCHEDULED/UNSCHEDULED: GREG WEICK: 6.44/2 = 8.44 HOURS MERLIN TACKETT: 5.3/3.18 = 8.48 HOURS JEFF ROSE: 7.68/.57 = 8.25 HOURS TOOLING DOWNTIME: 5.75 HOURS WORKCENTER LOGS: 6.25 HOURS
Diego | Maintenance | Y | PA 114: Was able to get the press to run in continuous, while running found that the lower right gib was getting hot, Superb rechecked the parallelism, and found the press to be out about .008, after being at Zero previous day, They leveled the ram again, and we ran in continuous for a while again, There was visible movement from left to right. We checked parallelism again, and the press was out again. We check the ram at 0/90/180/270, and determined that the press was out of time. Superb will need to correct this before moving forward. We also have an issue with building up pressure to the clutch. Aft Shift is rebuilding the Ross Valve. PA 118: The bolster will not lift out of the press, we swapped the pump, found that there was air being mixed in the Pump. We were able to get the cylinders up enough to get the bolster out, but they are still having issues pumping up all the way. We had to pump the pit out so we can get under the press to verify any leaks or loose fitting. This will be completed tomorrow morning. PA 119: Short Feed issues. We checked the feeder and could not determine any real causes for the short feeds. We played with the air pressure and changed out a pressure regulator. I am still troubleshooting this issue. Bay Chiller: The chiller faulted out. There was an overload condition. I reset the Overload, and the chiller ran the rest of the day. PS 66: Brake Monitor fault: Re-Calibrated Brake Monitor.
Yvonne | Quality Concerns |  | PA120 ¦ 724151H10B ¦ No new issues PA119 ¦ 724794H05C ¦ No new issues PA118 ¦ C93624 ¦ No new issues PA117 ¦ ¦ No new issues PA116 ¦ ¦ No new issues PA115 ¦ ¦ No new issues PA112 ¦ ¦ No new issues PA111 ¦ ¦ No new issues PA110 ¦ ¦ No new issues PA50 ¦ ¦ No new issues SSL ¦ 20007/8-AC ¦ No new issues Welding ¦ ¦ Customer ¦ ¦ No new issues Supplier ¦ ¦ No new issues Internal ¦ ¦ GM CCA - Shipments ¦ ¦ No issues to report

## Friday 9.25.26
Email daily to: Rav Sandhu, Sherree Martin, Ron Scott, Adrian Silva, Yvonne Rodriguez, Kofi Oduro, Melissa Gardynik; Scott Jones Email report daily at 5 pm.
EAP Daily Update - Friday 9.25.26 - Submitted to Executive Team by 5 pm
Responsible Party | Measurable | Status G/Y/R | Comments / Explanation
Nicole | EHS | G
Nicole | Staffing Issues | G | 2026 Q3 DL Requirement: 41 Staffing Changes: New Hire: Total EAP Employees minus LOA DL: 35 (1st 24 - 2nd 9) IDL: 25 (1st 18 - 2nd 7) Total Present: DL = 1st - 17, 2nd - 0 IDL = 18 (No 2nd shift) Planned Absenteeism: DL: 1st shift: Pam Bryson, Sophy Sou, Sue Bosman, Jason Faulkner, Chelsea Kreitner IDL: 1st shift: DL: 2nd Shift: IDL: 2nd Shift: Unplanned Absenteeism (call off/leave early): DL 1st shift - Tracey Stecker, Zaki Iskandaron IDL 1st Shift - DL 2nd Shift - IDL 2nd Shift: Other: LOA -DL -Jerry Weick (ERTW September - December), Merritt Higgins (TBD), HaiCi Huang (9/15-10/16)
| Current Year Program EOP | G | Guelph RDX - April 2026 GM A2SL (CT4) - June 2026 GM 610 (extended cargo van-U-Haul - Springfield) - September 2026
Michelle | Prem. Freight / Customer Notes | G | No premium freight.
Michelle | On Time Delivery | G | HBPO: Shipped 3000pcs to USF this week. Midwest working through 4000pcs that are on hold for paint concerns.
Michelle | Customer Invty Status Red = 1 day on hand Yellow = 2 days on hand Green = 3 days on hand |  | Customer | Program# | # of parts supplied
|  | G | Adient - Clanton | TYAA | 8 | Inventory coverage until 10/5
|  | G | Adient - Lakewood | TYAA | 20 | Inventory coverage until 10/1
|  | G |  | TYAA | 4 | Inventory coverage until 10/5
|  | G | GM - BWLGRN | TYAA | 8 | Inventory coverage until 10/1
|  | G |  | C1UL | 15 | Inventory coverage until 10/5
|  | G |  | Y1XX | 1 | Inventory coverage until 2/8
|  | G | GM-Factory Zero | BT1TL | 7 | Inventory coverage until 10/15
|  | G | GAP | D2UC | 1 | Inventory coverage until 10/14
|  | G |  | GMT610 | 8 | Inventory coverage until 10/2
|  | Y |  | WS | 2 | Inventory coverage until 9/28 17511's at Detroit Coatings.
|  | Y | OP M (HBPO) | RU | 3 | Inventory coverage until 9/25 Shipped 3k this week.
|  | G | Metalsa | UX71 | 2 | Inventory coverage until 10/5
|  | G | SLP | KM EJ | 5 | Inventory coverage until 11/16
|  | G | Stellantis | LB | 2 | Inventory coverage until 10/13
|  | G | Toyo-Imlay City | 500B | 10 | Inventory coverage until 10/2
|  | G | Toyo-Tennesee | L42P | 2 | Inventory coverage until 10/2
|  | Y | Voestalpine | G01 | 4 | Inventory coverage until 9/28. 307/308 running in PA118.
|  | G | Voestalpine | BR167 | 18 | Inventory coverage until 9/30 151 running in PA120.
Michele | SERVICE | G | ~84141998 and 85609492 shipped in full. ~23429897/23429898: GM Argentina order, waiting on commercial resolution. Hopefully by end of September. ~12608820: Steel received. Running in PA115 today, then heat treat and zinc. ~22799575: Pending direction/review of 1804 from GM CCA team. ~23445040: Pending direction/review of 1804 from GM CCA team. ~22717995: Pending direction/review of 1804 from GM CCA team.
Jeff Potter | Supplier Issues | G | No issues.
John W | Labor / Overtime | G | Held Jimmy (shipping) late due to second shift being off. Adient Ramos requested a last second expedite for PN 3696738 due to a plant loss. ETA of truck is 6pm.
John W. | Daily Efficiency 85%> = Green 69-84% = Yellow 69% < = Red |  | Work Center Group | % | Notes
88%
91%
88%
100%
John W | Downtime Analysis |  |  | TTL Hours | Reason Percentage | Notes
|  |  | Daily DT | 15.47
2nd shift 9/23: 1st shift 9/24:
John W | Operations Update - Critical Issues | G | 2nd shift 9/24: PA120: Lube pump dirty filter fault. Holes not pinning. (1.13hrs DT) PA119: Short feeding (15mins DT) PA116: Pilot release stopped working (25mins DT) 1st shift 9/25: PA119: Low air. End of coil issue getting through die (1.1hrs DT) PA118: Pumped out pit and worked on connections. Released to production at lunch. (4hrs DT) WC59: Adjustments after change over (1.06hrs DT) SSL: Hole burr, pulled die for tooling. (3.15hrs DT)
John W | MFG Mishit Reports | G | None
John W | Housekeeping | G | Cleaned trash/kitchen/conference room in office from audit. Cleaned bathrooms Cleaned lunch area Dumped trash Worked on removing dead pine tree branches. Only have the large trunk left to move.
John W | Change Overs
Scott | TOOLING | Y | 9/24 2ND SHIFT: C15013/15207: 100% - TRIM AND HOLE BURRS. 9.4 HOURS OPENING/CLOSING ADIENT DIES FOR PICS. 10.47 HOURS. C17510/511: 70% - FPM. 9.95 HOURS PRESS CALLS: PA120: C15112 - HOLES NOT PINNING. .9 HOURS. BO ADJUSTED TRAP GAGES AND THEN ALIGNMNET. SCHEDULED/UNSCHEDULED: JESSE DENNIS: 9.4/.9 = 10.3 HOURS JOHN GREEN: 10.47/0 = 10.47 HOURS ZACH BRAMIGK: 9.95/0 = 9.95 HOURS TOOLING DOWNTIME: .9 HOURS WORKCENTER LOGS: .93 HOURS 9/25 1ST SHIFT: C20002001: 30% - HOLE BURR/LONGER RANGE SENSORS. 3.65 HOURS C17510/511: 70% - FPM. 3.95 HOURS. 3693536: 100% - BURRS. 2.83 HOURS 3989858: 10% - BURR/FEELER FAIL. .93 HOURS MODIFY PINS FOR MMR AT PA114: 100% - 4.35 HOURS PRESS CALLS: PS94: HOLE BURR. 2.9 HOURS. MERLIN REPAIRED ONE HOLE BURR. GOT CALLED OUT AGAIN ABOUT 4 HOURS LATER FOR ANOTHER HOLE BURR. HAD TO PULL DIE TO GET TO PUNCH. SCHEDULED/UNSCHEDULED: GREG WEICK: 8.2/0 = 8.2 HOURS MERLIN TACKETT: 3.95/2.9 = 6.85 HOURS (LEFT EARLY) JEFF ROSE: 8.11/0 = 8.11 HOURS TOOLING DOWNTIME: 2.9 HOURS WORKCENTER LOGS: 3.15 HOURS
Diego | Maintenance | Y | PA 114: 9/25/26: Aft Shift rebuilt the ross valve last night but it is still blowing by, I will need to pull it down and go thru it. Superb started pulling the press apart to time the press. it appears to be about a 2-3 day job. PA 118: 9/25/26: Got the pit cleaned out, entered the pit, but the clearance on the side walls were to tight to visually see anything. I pressurized the system, checked, for any signs of leaks or blow by on the floor and walls. Built pressure past max, and removed the bleeder screws from the cylinder. Removed a lot of air in 3 of 4 of the cylinders. We then set the pressure at level and the cylinders were pumping up good. We could not determine if they would go down due to no weight being on them. The bolster was rolled in without incident. PA 119: Pilot Release will not open. Pulled all the lines, and checked the solenoid and cylinders, verified that the cylinders were good and not blowing by. Started putting everything back together one by one, and found that the pilot pressure regulator was blowing by. Swapped it out and pilot started working. E7-01: Leaking at the mast: found loose fitting. Tightened.
Yvonne | Quality Concerns |  | PA120 ¦ 724151H10B ¦ No new issues PA119 ¦ 724794H05C ¦ No new issues PA118 ¦ C93624 ¦ No new issues PA117 ¦ ¦ No new issues PA116 ¦ ¦ No new issues PA115 ¦ ¦ No new issues PA112 ¦ ¦ No new issues PA111 ¦ ¦ No new issues PA110 ¦ ¦ No new issues PA50 ¦ ¦ No new issues SSL ¦ 20007/8-AC ¦ No new issues Welding ¦ ¦ Customer ¦ T6H3CF198A ¦ Toyo found 7 Miss-hit parts. Requires sorting and an 8D here at EAP. If more parts are found at Toyo, sorting will be required there. Supplier ¦ ¦ No new issues Internal ¦ ¦ GM CCA - Shipments ¦ ¦ No issues to report