## Monday 9.21.26
Email daily to: Rav Sandhu, Sherree Martin, Ron Scott, Adrian Silva, Yvonne Rodriguez, Kofi Oduro, Melissa Gardynik; Scott Jones Email report daily at 5 pm.
GAP Daily Update - Monday 9.21.26 - Submitted to Executive Team by 5 pm
Responsible Party | Measurable | Status G/Y/R | Comments / Explanation
Nicole | EHS | G
Nicole | Staffing Issues | G | 2026 Q3 DL Requirement: 24 New Hires: Staff Changes: Termed Dylan Bishop & Joseph Childers Total GAP Employees MINUS LOA: DL: 14 IDL: 8 Total Present: DL = 14 IDL = 8 Planned Absenteeism (Adv notice/approval): DL: IDL: Unplanned Absenteeism DL: IDL: Other: LOA:
| Current Year Program EOP | G
Michelle | Prem. Freight / Customer Notes | G
Michelle | On Time Delivery | G
Michelle | Customer Invty Status Red = 1 day on hand Yellow = 2 days on hand Green = 3 days on hand |  | Customer | Program# | # of parts supplied
|  | G | GM-SH | C1UL | 2 | 613 -10/19 614-10/19
|  | G | GM-FZ | BT1FG | 2 | 936-1/11, 937-1/18
|  | G |  | BT1UG | 4 | 059-2/15/27, 060-3/1/27
|  | G | GM-WTZVL | GMT610- Hinge | 4 | 237-10/8 238-10/12, 282 - 10/6, 644 - 10/8
|  | G |  | GMT610 Roller Brkt | 3 | 340-10/12, 566-10/12, 567-10/7
|  | G |  | GMT610 Check | 1 | 133-10/2
|  | G | EAP | BT1YL | 4 | 12/1
|  | G | FCA | DT | 1 | 9/28
|  | G |  | WL | 2 | No requirements
|  | G |  | WS | 2 | 510 - 9/29 511 - 10/2
|  | G | CIE-MX | WK/WL | 1 | 10/26
|  | G | CIE-AH | WS | 1 | 10/26
|  | G | Kongsburg | K-T680/T880 | 1 | 9/25
|  | G | Lear - KY | WS | 1 | No requirements showing
|  | G | Lear - MX | T1XX | 2 | 193-9/30,199-10/12
|  | G | Metalsa A | JL-PHEV | 3 | JL-10/8 J9-10/1
|  | G | Metalsa O | JT | 2 | 027-10/26
|  | G | NYX - LIVONIA | S650 | 2 | 10/1
|  | G | Toyo | 500B | 13 | 9/28
|  | G | AGG | JL | 4 | Covered
Michele | SERVICE | G | GM-CCA - 13503000 on hold due to commercial issue
Jeff Potter | Supplier Issues | G | Target Steel, R5813 (material has zebra stripping, Target to issue RMA for the rejected material. Replacement material delivered on 9/11/26
John W | Labor / Overtime | G | Direct Labor - Joseph Childers - Quit - Dylan Bishop -Quit - Nicole engaged Indirect Labor - Open GL position - Under review Auto - 8 hours Die Set - 8 hours - Weld area - 8 hours W507 Hand MIG - 8 hours CNC - 8 hours Pack area - hours - Assembly - 8 hours Line Die - 8 hours -
John W. | Daily Efficiency 85%> = Green 69-84% = Yellow 69% < = Red |  | Work Center Group | % | Notes
90%
98%
93%
98%
John W | Downtime Analysis |  |  | TTL Hours | Reason Percentage | Notes
|  |  | Daily DT | 15.47
610E down 39 minutes - A838 down 36 minutes - CNC down 30 minutes - broken cutter - W516
P102
P102 Die change -
John W | Operations Update - Critical Issues | Y | Auto area - P106 Down Main Motor Drive - Diego to report out P100 C193AA - In die set - Currently at 875 tons with high lead readings - Team engaged P102 - P6219 - Running P106 - Down - Drive parameters lost from repair - Diego engaged with Excel for support - No timing provided P108 - C2217 - 6K run completed - Dispatch clear - Reviewing P109 - C3523 - 5K completed - Reviewing next in P112 - C2235/2236 - 10K run completed - C3115/65 - Running P114 - C44897/64738 - 12K run completed -Reviewing P115 - Press clearedP116 - Press cleared Line Die - No major concerns PS202 - 3388-30 - Running PS205 - GM610 - 84509133 - Run completed PS209 - 5122-0-10 - 3K run completed PS218 - 5126-6-10/20- Run completed PS219 - 5128-7-10/20 - Not scheduled Weld area - Excessive Downtime W516 Inconsistent parts - Team adjusting CNC - 5816-20 - Running - Operator in training W05- 5122 - FPA obtained - Ready to run W507 - 5104/5 - Running W513 - 20019-10 - Not scheduled W514 - 69573-10 - Not scheduled W515 - 3388-10 - Running W516 - 5816-10 - Down - Team engaged with adjustments for failing fixture checks Assembly - A895 - 1220-10-10 -Try-out and process review - 175 pair completed - Team to review any concerns - Reviewing presentation provided by Angel Sanchez A886 - 23186613 - Run completed- 23186614 - Run completed A500 - C20001010 - Running A838 - 22934282 - Run completed - A839 - 84141644 - Run completed - A837- 15150237 - Run completed 610 E , F , G - 610F - 20814566-Not scheduled - 610G 15837340- Not scheduled - 610 E - Not scheduled A891 - run completed A892 - 6059-10 - Running - 6060-10 - Not scheduled A893 - 86518936 - Running A894 - scheduled 09/10 - A889 - A890 - Run completed MAN - 4615-3 - Not scheduled
John W | MFG Mishit Reports | G
John W | Housekeeping | Y | Floor scrubber - Up and running - John W working on training plan completed - Next will train operators Housekeeping projects - Running floor scrubber EOS Daily housekeeping - Completed
John W | Change Overs | G | P100 - Die change P112 - Die change
Scott | TOOLING | G | C199AA-11. Leroy should have the form done Monday. Than will send to heat treat and coating C5126-6 Waiting on side forms to come back from eifler than will reassemble C51220-21 Underbody die is opened in the tool room. Checking lead hits on the forms and breakage on the trims Scott Scheduled 9 hours Unscheduled 0 hours Nick Scheduled 8 hours Unscheduled 0 hours
Diego | Maintenance | G | PM's on air compressors, dryers, waste water & drums. Full PM on compressor 2( separator change, oil change, replaced all air filters, oil filters)
Yvonne | Quality Concerns |  | ¦ ¦ No new issues. Sent the new gage and parts to EAP for verification.

## Tuesday 9.22.26
Email daily to: Rav Sandhu, Sherree Martin, Ron Scott, Adrian Silva, Yvonne Rodriguez, Kofi Oduro, Melissa Gardynik; Scott Jones Email report daily at 5 pm.
GAP Daily Update - Tuesday 9.22.26 - Submitted to Executive Team by 5 pm
Responsible Party | Measurable | Status G/Y/R | Comments / Explanation
Nicole | EHS | G
Nicole | Staffing Issues | G | 2026 Q3 DL Requirement: 24 New Hires: Staff Changes: Total GAP Employees MINUS LOA: DL: 14 IDL: 8 Total Present: DL = 13 IDL = 7 Planned Absenteeism (Adv notice/approval): DL: IDL: Nick Halatsis Unplanned Absenteeism DL: Angee Sears IDL: Other: LOA:
| Current Year Program EOP | G
Michelle | Prem. Freight / Customer Notes | G
Michelle | On Time Delivery | G
Michelle | Customer Invty Status Red = 1 day on hand Yellow = 2 days on hand Green = 3 days on hand |  | Customer | Program# | # of parts supplied
|  | G | GM-SH | C1UL | 2 | 613 -10/19 614-10/26
|  | G | GM-FZ | BT1FG | 2 | 936-1/11, 937-1/25
|  | G |  | BT1UG | 4 | 059-3/1/27, 060-3/8/27
|  | G | GM-WTZVL | GMT610- Hinge | 4 | 237-10/8 238-10/14, 282 - 10/9, 644 - 10/8
|  | G |  | GMT610 Roller Brkt | 3 | 340-10/14, 566-10/13, 567-10/16
|  | G |  | GMT610 Check | 1 | 133-10/7
|  | G | EAP | BT1YL | 4 | 12/1
|  | G | FCA | DT | 1 | 9/28
|  | G |  | WL | 2 | No requirements
|  | G |  | WS | 2 | 510 - 10/5, 511 - 10/2
|  | G | CIE-MX | WK/WL | 1 | 10/26
|  | G | CIE-AH | WS | 1 | 10/26
|  | G | Kongsburg | K-T680/T880 | 1 | 9/25
|  | G | Lear - KY | WS | 1 | No requirements showing
|  | G | Lear - MX | T1XX | 2 | 193-9/30,199-10/12
|  | G | Metalsa A | JL-PHEV | 3 | JL-10/29 J9-10/1
|  | G | Metalsa O | JT | 2 | 027-10/26
|  | G | NYX - LIVONIA | S650 | 2 | 10/1
|  | G | Toyo | 500B | 13 | 10/12
|  | G | AGG | JL | 4 | Covered
Michele | SERVICE | G | GM-CCA - 13503000 on hold due to commercial issue
Jeff Potter | Supplier Issues | G | Target Steel, R5813 (material has zebra stripping, Target to issue RMA for the rejected material. Replacement material delivered on 9/11/26
John W | Labor / Overtime | G | Direct Labor - Angie Sears - call off Indirect Labor - Open GL position - None Auto - 8 hours Die Set - 8 hours - Weld area - 8 hours W507 Hand MIG - 8 hours CNC - 8 hours Pack area - hours - Assembly - 8 hours Line Die - 8 hours -
John W. | Daily Efficiency 85%> = Green 69-84% = Yellow 69% < = Red |  | Work Center Group | % | Notes
45%
98%
99%
99%
John W | Downtime Analysis |  |  | TTL Hours | Reason Percentage | Notes
|  |  | Daily DT | 15.47
P106 - Drive install - P100 checking if ram was level
P100 - Holes not pinning
P100
John W | Operations Update - Critical Issues | Y | Auto area - P106 Down 6 hours Main Motor Drive - Released to production P100 C193AA - Down 1 hour ram being checked for level - Down 2 hours - Holes not pinning - FPA obtained P102 - P6219 - 10K run completed P106 - C47054/64722 - In die set P108 - C2217 - 6K run completed - Dispatch clear - Reviewing P109 - C3523 - 5K completed - Reviewing next in P112 - C3115/65 - 14K run completed P114 - C44897/64738 - Going in next P115 - Press clearedP116 - Press cleared Line Die - No major concerns PS202 - 3388-30 - Run completed PS205 - GM610 - 84509133 - Run completed PS209 - 5122-0-10 - 3K run completed PS218 - 5126-6-10/20- Run completed PS219 - 5128-7-10/20 - Not scheduled Weld area - Excessive Downtime W516 Inconsistent parts - Team adjusting CNC - 5816-20 - Running - Operator in training W05- 5122 - FPA obtained - Ready to run W507 - 5104/5 - Running W513 - 20019-10 - Not scheduled W514 - 69573-10 - Not scheduled W515 - 3388-20 - Running W516 - 5816-10 - Down - Team engaged with adjustments for failing fixture checks Assembly - A895 - 1220-10-10 -Try-out and process review - 175 pair completed - Team to review any concerns - Reviewing presentation provided by Angel Sanchez A886 - 23186613 - Run completed- 23186614 - Run completed A500 - C20001010 - Running A838 - 22934282 - Run completed - A839 - 84141644 - Run completed - A837- 15150237 - Run completed 610 E , F , G - 610F - 20814566-Not scheduled - 610G 15837340- Not scheduled - 610 E - Not scheduled A891 - run completed A892 - 6059-10 - Running - 6060-10 - Not scheduled A893 - 86518936 - Running A894 - scheduled 09/10 - A889 - A890 - Run completed MAN - 4615-3 - Not scheduled
John W | MFG Mishit Reports | G
John W | Housekeeping | Y | Floor scrubber - Up and running - John W working on training plan completed - Next will train operators Housekeeping projects - Running floor scrubber EOS Daily housekeeping - Completed
John W | Change Overs | G | P100 - Die change P112 - Die change
Scott | TOOLING | G | C199AA-11. Leroy is still working on the form C5126-6 Side forms are back. Need to install and reassemble the die C51220-21 Underbody die is opened in the tool room. Checking lead hits on the forms and breakage on the trims Took pics to make another power point on breakage and lead hits. Started bringing in Inalfa dies and opening and pre staging for Friday review at 10am Scott Scheduled 9 hours Unscheduled 0 hours Nick Vacation day
Diego | Maintenance | G | PM's on welders complete.
Yvonne | Quality Concerns |  | ¦ ¦ No new issues. Sent the new gage and parts to EAP for verification.

## Wednesday 9.23.26
Email daily to: Rav Sandhu, Sherree Martin, Ron Scott, Adrian Silva, Yvonne Rodriguez, Kofi Oduro, Melissa Gardynik; Scott Jones Email report daily at 5 pm.
GAP Daily Update - Wednesday 9.23.26 - Submitted to Executive Team by 5 pm
Responsible Party | Measurable | Status G/Y/R | Comments / Explanation
Nicole | EHS | G
Nicole | Staffing Issues | G | 2026 Q3 DL Requirement: 24 New Hires: Staff Changes: Total GAP Employees MINUS LOA: DL: 14 IDL: 8 Total Present: DL = 14 IDL = 8 Planned Absenteeism (Adv notice/approval): DL: IDL: Unplanned Absenteeism DL: IDL: Other: LOA:
| Current Year Program EOP | G
Michelle | Prem. Freight / Customer Notes | G
Michelle | On Time Delivery | G
Michelle | Customer Invty Status Red = 1 day on hand Yellow = 2 days on hand Green = 3 days on hand |  | Customer | Program# | # of parts supplied
|  | G | GM-SH | C1UL | 2 | 613 -10/19 614-10/26
|  | G | GM-FZ | BT1FG | 2 | 936-1/11, 937-1/25
|  | G |  | BT1UG | 4 | 059-3/1/27, 060-3/8/27
|  | G | GM-WTZVL | GMT610- Hinge | 4 | 237-10/8 238-10/14, 282 - 10/9, 644 - 10/8
|  | G |  | GMT610 Roller Brkt | 3 | 340-10/14, 566-10/13, 567-10/16
|  | G |  | GMT610 Check | 1 | 133-10/7
|  | G | EAP | BT1YL | 4 | 12/1
|  | G | FCA | DT | 1 | 9/28
|  | G |  | WL | 2 | No requirements
|  | G |  | WS | 2 | 510 - 10/5, 511 - 10/2
|  | G | CIE-MX | WK/WL | 1 | No requirements showing
|  | G | CIE-AH | WS | 1 | 11/9
|  | G | Kongsburg | K-T680/T880 | 1 | 10/2
|  | G | Lear - KY | WS | 1 | No requirements showing
|  | G | Lear - MX | T1XX | 2 | 193-9/30,199-10/12
|  | G | Metalsa A | JL-PHEV | 3 | JL-10/29 J9-10/1
|  | G | Metalsa O | JT | 2 | 027-10/26
|  | G | NYX - LIVONIA | S650 | 2 | 10/1
|  | G | Toyo | 500B | 13 | 10/12
|  | G | AGG | JL | 4 | Covered
Michele | SERVICE | G | GM-CCA - 13503000 on hold due to commercial issue
Jeff Potter | Supplier Issues | G | Target Steel, R5813 (material has zebra stripping, Target to issue RMA for the rejected material. Replacement material delivered on 9/11/26
John W | Labor / Overtime | G | Direct Labor - Indirect Labor - Diego at EAP Open GL position - None Auto - 8 hours Die Set - 8 hours - Weld area - 8 hours W507 Hand MIG - 8 hours CNC - 8 hours Pack area - hours - Assembly - 8 hours Line Die - 8 hours -
John W. | Daily Efficiency 85%> = Green 69-84% = Yellow 69% < = Red |  | Work Center Group | % | Notes
72%
98%
99%
95%
John W | Downtime Analysis |  |  | TTL Hours | Reason Percentage | Notes
|  |  | Daily DT | 15.47
W516 - Failed pin check - Adjusted
P100 - Holes not pinning
P100 - set up adjustments for FPA - P106 Die change
W515 - C/O
John W | Operations Update - Critical Issues | G | Auto area - P100 and P106 - Both back online P100 C193AA - Down 2.5 hours - Holes not pinning - Running P102 - P6219 - 10K run completed P106 - C47054/64722 - FPA obtained - Running P108 - C2217 - 6K run completed - Dispatch clear - Reviewing P109 - C3523 - 5K completed - Reviewing next in P112 - C3115/65 - 14K run completed P114 - C44897/64738 - Going in next P115 - Press clearedP116 - Press cleared Line Die - No major concerns PS202 - 3388-30 - Running PS205 - GM610 - 84509133 - Run completed PS209 - 5122-0-10 - 3K run completed PS218 - 5126-6-10/20- Run completed PS219 - 5128-7-10/20 - Not scheduled Weld area - Excessive Downtime W516 Inconsistent parts - Team adjusting CNC - 5816-20 - Running - Operator in training W05- 5122 - Running W507 - 5104/5 - Running W513 - 20019-10 - Not scheduled W514 - 69573-10 - Not scheduled W515 - 3388-20 - Run completed - C/O to 3388-10 W516 - 5816-10 - Running - Team monitoring Assembly - A895 - 1220-10-10 -Try-out and process review - 175 pair completed - Team to review any concerns - Reviewing presentation provided by Angel Sanchez A886 - 23186613 - Run completed- 23186614 - Run completed A500 - C20001010 - Not scheduled A838 - 22934282 - Run completed - A839 - 84141644 - Run completed - A837- 15150237 - Run completed 610 E , F , G - 610F - 20814566-Not scheduled - 610G 15837340- Not scheduled - 610 E - Not scheduled A891 - run completed A892 - 6059-10 - Running - 6060-10 - Not scheduled A893 - 86518936 - Running A894 - scheduled 09/10 - A889 - A890 - Run completed MAN - 4615-3 - Not scheduled
John W | MFG Mishit Reports | G
John W | Housekeeping | Y | Floor scrubber - Up and running - John W working on training plan - completed - Next will train operators Housekeeping projects - Running floor scrubber EOS Daily housekeeping - Completed
John W | Change Overs | G | P100 - Adjustments for FPA P106 - Die change
Scott | TOOLING | G | C199AA-11. Leroy is still working on the form C5126-6 Side forms are back. Need to install and reassemble the die C51220-21 Underbody die is opened in the tool room. Checking lead hits on the forms and breakage on the trims Took pics to make another power point on breakage and lead hits. We have 1 more inalfa die to bring in. All the rest are opened and staged inside the shop C193AA-11 was down for 3 holes not pinning. Made adjustments and they all pin now. Scott Scheduled 8 hours Unscheduled 1 hour Nick Scheduled 9 hours Unscheduled 1 hour
Diego | Maintenance | G | PM's on welders complete.
Yvonne | Quality Concerns |  | ¦ ¦ No new issues. Working on PPAP's for Stellantis.

## Thursday 9.24.26
Email daily to: Rav Sandhu, Sherree Martin, Ron Scott, Adrian Silva, Yvonne Rodriguez, Kofi Oduro, Melissa Gardynik; Scott Jones Email report daily at 5 pm.
GAP Daily Update - Thursday 9.24.26 - Submitted to Executive Team by 5 pm
Responsible Party | Measurable | Status G/Y/R | Comments / Explanation
Nicole | EHS | G
Nicole | Staffing Issues | G | 2026 Q3 DL Requirement: 24 New Hires: Staff Changes: Total GAP Employees MINUS LOA: DL: 14 IDL: 8 Total Present: DL = 14 IDL = 8 Planned Absenteeism (Adv notice/approval): DL: IDL: Unplanned Absenteeism DL: IDL: Other: LOA:
| Current Year Program EOP | G
Michelle | Prem. Freight / Customer Notes | G
Michelle | On Time Delivery | G
Michelle | Customer Invty Status Red = 1 day on hand Yellow = 2 days on hand Green = 3 days on hand |  | Customer | Program# | # of parts supplied
|  | G | GM-SH | C1UL | 2 | 613 -10/19 614-10/26
|  | G | GM-FZ | BT1FG | 2 | 936-1/11, 937-1/25
|  | G |  | BT1UG | 4 | 059-3/1/27, 060-3/8/27
|  | G | GM-WTZVL | GMT610- Hinge | 4 | 237-10/8 238-10/14, 282 - 10/9, 644 - 10/8
|  | G |  | GMT610 Roller Brkt | 3 | 340-10/14, 566-10/13, 567-10/16
|  | G |  | GMT610 Check | 1 | 133-10/7
|  | G | EAP | BT1YL | 4 | 12/1
|  | G | FCA | DT | 1 | 10/1
|  | G |  | WL | 2 | No requirements
|  | G |  | WS | 2 | 510 - 10/8, 511 - 10/2
|  | G | CIE-MX | WK/WL | 1 | No requirements showing
|  | G | CIE-AH | WS | 1 | 11/9
|  | G | Kongsburg | K-T680/T880 | 1 | 10/2
|  | G | Lear - KY | WS | 1 | No requirements showing
|  | G | Lear - MX | T1XX | 2 | 193-9/30,199-10/12
|  | G | Metalsa A | JL-PHEV | 3 | JL-10/29 J9-10/1
|  | G | Metalsa O | JT | 2 | 027-10/26
|  | G | NYX - LIVONIA | S650 | 2 | 10/1
|  | G | Toyo | 500B | 13 | 10/12
|  | G | AGG | JL | 4 | Covered
Michele | SERVICE | G | GM-CCA - 13503000 on hold due to commercial issue
Jeff Potter | Supplier Issues | G | Target Steel, R5813 (material has zebra stripping, Target to issue RMA for the rejected material. Replacement material delivered on 9/11/26
John W | Labor / Overtime | G | Direct Labor - All here Indirect Labor - Open GL position - None Auto - 8 hours Die Set - 8 hours - Weld area - 8 hours W507 Hand MIG - 8 hours CNC - 8 hours Pack area - hours - Assembly - 8 hours Line Die - 8 hours -
John W. | Daily Efficiency 85%> = Green 69-84% = Yellow 69% < = Red |  | Work Center Group | % | Notes
77%
98%
91%
94%
John W | Downtime Analysis |  |  | TTL Hours | Reason Percentage | Notes
|  |  | Daily DT | 15.47
W516 - Failed pin check - P100 Feeder pendant repair - CNC Down 40 minutes - broken cutter
P100 - Holes not pinning
P114 - Die change
W515 - C/O
John W | Operations Update - Critical Issues | Y | Auto area - P100 C193AA - Down 1 hour for feeder pendant repair - Ran 1 coil of good material with no issues - Tried coil on hold for splits and lamination - Unable to run due to excessive splitting - Team engaged - Replacement steel to deliver 09/25 at 1pm P102 - P6219 - 10K run completed P106 - C47054/64722 - Running P108 - C2217 - 6K run completed - Dispatch clear - Reviewing P109 - C3523 - 5K completed - Reviewing next in P112 - C3115/65 - 14K run completed P114 - C44897/64738 - FPA obtained - 10/01 run date P115 - Press clearedP116 - Press cleared Line Die - No major concerns PS202 - 3388-30 - Running PS205 - GM610 - 84509133 - Run completed PS209 - 5122-0-10 - 3K run completed PS218 - 5126-6-10/20- Run completed PS219 - 5128-7-10/20 - Not scheduled Weld area - Excessive Downtime W516 Inconsistent parts - Team adjusting CNC - 5816-20 - Running - Down 1 hour for cutter change and coolant mixing W05- 5122 - Running W507 - 5104/5 - Running W513 - 20019-10 - Not scheduled W514 - 69573-10 - Not scheduled W515 - 3388-10 - Running W516 - 5816-10 - Running - Team monitoring Assembly - A895 - 1220-10-10 -Try-out and process review - 175 pair completed - Team to review any concerns - Reviewing presentation provided by Angel Sanchez A886 - 23186613 - Run completed- 23186614 - Run completed A500 - C20001010 - Not scheduled A838 - 22934282 - Run completed - A839 - 84141644 - Run completed - A837- 15150237 - Run completed 610 E , F , G - 610F - 20814566-Not scheduled - 610G 15837340- Not scheduled - 610 E - Not scheduled A891 - run completed A892 - 6059-10 - Running - 6060-10 - Not scheduled A893 - 86518936 - Running A894 - scheduled 09/10 - A889 - A890 - Run completed MAN - 4615-3 - Not scheduled
John W | MFG Mishit Reports | G
John W | Housekeeping | Y | Floor scrubber - Up and running - John W working on training plan - completed - Next will train operators Housekeeping projects - Running floor scrubber EOS Daily housekeeping - Completed
John W | Change Overs | G | P100 - Tried to run rejected material - Excessive splits and Lamination P114 - Die change
Scott | TOOLING | G | C199AA-11. Leroy is still working on the form C5126-6 Installed new forms. Entered die. Reassembled. Sent back to production floor C51220-21 Underbody die is opened in the tool room. Checking lead hits on the forms and breakage on the trims Took pics to make another power point on breakage and lead hits. All inalfa dies are opened and pre staged inside the shop for tomorrows review Scott Scheduled 9 hours Unscheduled 0 hour Nick Scheduled 10 hours Unscheduled 0 hour
Diego | Maintenance | G | PM's on welders complete. Wm516: adjust for consistency.
Yvonne | Quality Concerns |  | ¦ ¦ No new issues. Working on PPAP's for Stellantis.

## Friday 9.25.26
Email daily to: Rav Sandhu, Sherree Martin, Ron Scott, Adrian Silva, Yvonne Rodriguez, Kofi Oduro, Melissa Gardynik; Scott Jones Email report daily at 5 pm.
GAP Daily Update - Friday 9.25.26 - Submitted to Executive Team by 5 pm
Responsible Party | Measurable | Status G/Y/R | Comments / Explanation
Nicole | EHS | G
Nicole | Staffing Issues | G | 2026 Q3 DL Requirement: 24 New Hires: Staff Changes: Total GAP Employees MINUS LOA: DL: 14 IDL: 8 Total Present: DL = 0 IDL = 0 Planned Absenteeism (Adv notice/approval): DL: IDL: Unplanned Absenteeism DL: IDL: Other: LOA:
| Current Year Program EOP | G
Michelle | Prem. Freight / Customer Notes | G
Michelle | On Time Delivery | G
Michelle | Customer Invty Status Red = 1 day on hand Yellow = 2 days on hand Green = 3 days on hand |  | Customer | Program# | # of parts supplied
|  | G | GM-SH | C1UL | 2 | 613 -10/19 614-10/26
|  | G | GM-FZ | BT1FG | 2 | 936-1/11, 937-1/25
|  | G |  | BT1UG | 4 | 059-3/1/27, 060-3/8/27
|  | G | GM-WTZVL | GMT610- Hinge | 4 | 237-10/8 238-10/14, 282 - 10/9, 644 - 10/8
|  | G |  | GMT610 Roller Brkt | 3 | 340-10/14, 566-10/13, 567-10/16
|  | G |  | GMT610 Check | 1 | 133-10/7
|  | G | EAP | BT1YL | 4 | 12/1
|  | G | FCA | DT | 1 | 10/1
|  | G |  | WL | 2 | No requirements
|  | G |  | WS | 2 | 510 - 10/8, 511 - 10/2
|  | G | CIE-MX | WK/WL | 1 | No requirements showing
|  | G | CIE-AH | WS | 1 | 11/9
|  | G | Kongsburg | K-T680/T880 | 1 | 10/2
|  | G | Lear - KY | WS | 1 | No requirements showing
|  | G | Lear - MX | T1XX | 2 | 193-9/30,199-10/12
|  | G | Metalsa A | JL-PHEV | 3 | JL-10/29 J9-10/1
|  | G | Metalsa O | JT | 2 | 027-10/26
|  | G | NYX - LIVONIA | S650 | 2 | 10/1
|  | G | Toyo | 500B | 13 | 10/12
|  | G | AGG | JL | 4 | Covered
Michele | SERVICE | G | GM-CCA - 13503000 on hold due to commercial issue
Jeff Potter | Supplier Issues | G | Target Steel, R5813 (material has zebra stripping, Target to issue RMA for the rejected material. Replacement material delivered on 9/11/26
John W | Labor / Overtime | G | Direct Labor - All here Indirect Labor - Open GL position - None Auto - 8 hours Die Set - 8 hours - Weld area - 8 hours W507 Hand MIG - 8 hours CNC - 8 hours Pack area - hours - Assembly - 8 hours Line Die - 8 hours -
John W. | Daily Efficiency 85%> = Green 69-84% = Yellow 69% < = Red |  | Work Center Group | % | Notes
77%
98%
91%
94%
John W | Downtime Analysis |  |  | TTL Hours | Reason Percentage | Notes
|  |  | Daily DT | 15.47
W516 - Failed pin check - P100 Feeder pendant repair - CNC Down 40 minutes - broken cutter
P100 - Holes not pinning
P114 - Die change
W515 - C/O
John W | Operations Update - Critical Issues | Y | Auto area - P100 C193AA - Down 1 hour for feeder pendant repair - Ran 1 coil of good material with no issues - Tried coil on hold for splits and lamination - Unable to run due to excessive splitting - Team engaged - Replacement steel to deliver 09/25 at 1pm P102 - P6219 - 10K run completed P106 - C47054/64722 - Running P108 - C2217 - 6K run completed - Dispatch clear - Reviewing P109 - C3523 - 5K completed - Reviewing next in P112 - C3115/65 - 14K run completed P114 - C44897/64738 - FPA obtained - 10/01 run date P115 - Press clearedP116 - Press cleared Line Die - No major concerns PS202 - 3388-30 - Running PS205 - GM610 - 84509133 - Run completed PS209 - 5122-0-10 - 3K run completed PS218 - 5126-6-10/20- Run completed PS219 - 5128-7-10/20 - Not scheduled Weld area - Excessive Downtime W516 Inconsistent parts - Team adjusting CNC - 5816-20 - Running - Down 1 hour for cutter change and coolant mixing W05- 5122 - Running W507 - 5104/5 - Running W513 - 20019-10 - Not scheduled W514 - 69573-10 - Not scheduled W515 - 3388-10 - Running W516 - 5816-10 - Running - Team monitoring Assembly - A895 - 1220-10-10 -Try-out and process review - 175 pair completed - Team to review any concerns - Reviewing presentation provided by Angel Sanchez A886 - 23186613 - Run completed- 23186614 - Run completed A500 - C20001010 - Not scheduled A838 - 22934282 - Run completed - A839 - 84141644 - Run completed - A837- 15150237 - Run completed 610 E , F , G - 610F - 20814566-Not scheduled - 610G 15837340- Not scheduled - 610 E - Not scheduled A891 - run completed A892 - 6059-10 - Running - 6060-10 - Not scheduled A893 - 86518936 - Running A894 - scheduled 09/10 - A889 - A890 - Run completed MAN - 4615-3 - Not scheduled
John W | MFG Mishit Reports | G
John W | Housekeeping | Y | Floor scrubber - Up and running - John W working on training plan - completed - Next will train operators Housekeeping projects - Running floor scrubber EOS Daily housekeeping - Completed
John W | Change Overs | G | P100 - Tried to run rejected material - Excessive splits and Lamination P114 - Die change
Scott | TOOLING | G | C199AA-11. Leroy finished the form this morning and was sent out to heat treat C51220-21 Made a power point for Die Entering Tryout from what we found so far. Sent to Ron Scott and Chris Richards Inalfa was here to look at their dies. In process of working with Angelo to close them all back up Scott Scheduled 9 hours Unscheduled 0 hour Nick Off on Fridays
Diego | Maintenance | G | PM's on welders complete. Wm516: adjust for consistency.
Yvonne | Quality Concerns |  | ¦ ¦ No new issues. Working on PPAP's for Stellantis.