## Monday 8.17.26
Email daily to: Rav Sandhu, Sherree Martin, Ron Scott, Adrian Silva, Yvonne Rodriguez, Kofi Oduro, Melissa Gardynik; Scott Jones Email report daily at 5 pm.
SLP Daily Update - Monday 8.17.26 - Submitted to Executive Team by 5 pm
Responsible Party | Measurable | Status G/Y/R | Comments / Explanation
Nicole | EHS | G | Safety: 948 days without an incident
Nicole | Staffing Issues | G | 2nd Quarter 2026 DL Requirements: 9 SLP DL = N/A IDL = N/A Planned Absenteeism (Adv notice/approval): DL : N/A IDL: N/A Unplanned Absenteeism (call off/leave early): DL =N/A IDL =N/A
| Current Year Program EOP | G | TK MX: A2LL EOP Jul 2026 Zoppas: PTAC EOP Dec 2026
Michelle | Prem. Freight / Customer Notes | G | No issues regarding raw material availability.
Michelle | On Time Delivery | G | No Issues.
Michelle | Customer Invty Status Red = 1 day on hand Yellow = 2 days on hand Green = 3 days on hand |  | Customer | Program# | # of parts supplied
|  | G | Kayser | VW | 1 | Inventory coverage until Aug 27th. They decreased requirements
|  | G | Stellantis | T1XX | 4 | Inventory coverage until Sep 02nd.
|  | G |  | EJ KM | 3 | Inventory coverage until Sept 3rd. We continue having daily requirements adjustments
|  | G | Zoppas | LB | 2 | There are no requirements until January 2027
|  | G |  | GM A2XX | 1 | Inventory coverage until Aug 28th.
|  | G |  | GE PTAC | 2 | Inventory coverage until Sep 11th.
|  | G | Flexitech | "FORD-CD6 GM-BT1XX" | 8 | Inventory coverage until Sep 03th
Michele | SERVICE
Jeff Potter | Supplier Issues | G | No issues regarding raw material availability.
John W | Labor / Overtime | G | Packaging staff needed
John W. | Daily Efficiency 85%> = Green 69-84% = Yellow 69% < = Red | G | Work Center Group | % | Notes
80%
0%
0%
100%
John W | Downtime Analysis |  |  | TTL Hours | Reason Percentage | Notes
|  |  | Daily DT | 15.47
No scheduled
No scheduled
No scheduled
No scheduled
No scheduled
John W | Operations Update - Critical Issues | Y | P11 No scheduled. P21 No scheduled. P41 830/831 for NYX. P42 55237/38 for Zoppas, no critical issues. P43 2919 for TK MX no critical issues WC01 853 for stellantis. WC02 No scheduled. PW01 853 for Stellantis no critical issues RW01 No scheduled
John W | MFG Mishit Reports | G | No Issues.
John W | Housekeeping | G | cleaned bathrooms cleaned lunch area dumped trash cleaned water from floors
John W | Change Overs | G | No Issues .
Scott | TOOLING | G | Die 225 on maintenance due to slight adjusments.
Diego | Maintenance | G | PA011 preventive maintenance, this machine will be used for Op Mobility clinching parts
Yvonne | Quality Concerns |  | ¦ ¦ External- No Concerns ¦ ¦ External- No Concerns

## Tuesday 8.18.26
Email daily to: Rav Sandhu, Sherree Martin, Ron Scott, Adrian Silva, Yvonne Rodriguez, Kofi Oduro, Melissa Gardynik; Scott Jones Email report daily at 5 pm.
SLP Daily Update - Tuesday 8.18.26 - Submitted to Executive Team by 5 pm
Responsible Party | Measurable | Status G/Y/R | Comments / Explanation
Nicole | EHS | G | Safety: 949 days without an incident
Nicole | Staffing Issues | G | 2nd Quarter 2026 DL Requirements: 9 SLP DL = N/A IDL = N/A Planned Absenteeism (Adv notice/approval): DL : N/A IDL: N/A Unplanned Absenteeism (call off/leave early): DL =N/A IDL =N/A
| Current Year Program EOP | G | TK MX: A2LL EOP Jul 2026 Zoppas: PTAC EOP Dec 2026
Michelle | Prem. Freight / Customer Notes | G | No issues regarding raw material availability.
Michelle | On Time Delivery | G | No Issues.
Michelle | Customer Invty Status Red = 1 day on hand Yellow = 2 days on hand Green = 3 days on hand |  | Customer | Program# | # of parts supplied
|  | G | Kayser | VW | 1 | Inventory coverage until Aug 27th. They decreased requirements
|  | G | Stellantis | T1XX | 4 | Inventory coverage until Sep 02nd.
|  | G |  | EJ KM | 3 | Inventory coverage until Sept 3rd. We continue having daily requirements adjustments
|  | G | Zoppas | LB | 2 | There are no requirements until January 2027
|  | G |  | GM A2XX | 1 | Inventory coverage until Aug 28th.
|  | G |  | GE PTAC | 2 | Inventory coverage until Sep 11th.
|  | G | Flexitech | "FORD-CD6 GM-BT1XX" | 8 | Inventory coverage until Sep 03th
Michele | SERVICE
Jeff Potter | Supplier Issues | G | No issues regarding raw material availability.
John W | Labor / Overtime | G | Packaging staff needed
John W. | Daily Efficiency 85%> = Green 69-84% = Yellow 69% < = Red | G | Work Center Group | % | Notes
91%
0%
84%
100%
John W | Downtime Analysis |  |  | TTL Hours | Reason Percentage | Notes
|  |  | Daily DT | 15.47
No scheduled
No scheduled
No scheduled
No scheduled
No scheduled
John W | Operations Update - Critical Issues | Y | P11 No scheduled. P21 No scheduled. P41 830/831 for NYX. P42 55237/38 for Zoppas, no critical issues. P43 2919 for TK MX no critical issues WC01 853 for stellantis. WC02 No scheduled. PW01 853 for Stellantis no critical issues RW01 No scheduled
John W | MFG Mishit Reports | G | No Issues.
John W | Housekeeping | G | cleaned bathrooms cleaned lunch area dumped trash cleaned water from floors
John W | Change Overs | G | No Issues .
Scott | TOOLING | G | Die 225 on maintenance due to slight adjusments.
Diego | Maintenance | G | PA011 preventive maintenance, this machine will be used for Op Mobility clinching parts
Yvonne | Quality Concerns |  | ¦ ¦ External- No Concerns ¦ ¦ External- No Concerns

## Wednesday 8.19.26
Email daily to: Rav Sandhu, Sherree Martin, Ron Scott, Adrian Silva, Yvonne Rodriguez, Kofi Oduro, Melissa Gardynik; Scott Jones Email report daily at 5 pm.
SLP Daily Update - Wednesday 8.19.26 - Submitted to Executive Team by 5 pm
Responsible Party | Measurable | Status G/Y/R | Comments / Explanation
Nicole | EHS | G | Safety: 953 days without an incident
Nicole | Staffing Issues | G | 2nd Quarter 2026 DL Requirements: 9 SLP DL = N/A IDL = N/A Planned Absenteeism (Adv notice/approval): DL : N/A IDL: Mercedes Suarez Unplanned Absenteeism (call off/leave early): DL =N/A IDL =N/A
| Current Year Program EOP | G | TK MX: A2LL EOP Jul 2026 Zoppas: PTAC EOP Dec 2026
Michelle | Prem. Freight / Customer Notes | G | No issues regarding raw material availability.
Michelle | On Time Delivery | G | No Issues.
Michelle | Customer Invty Status Red = 1 day on hand Yellow = 2 days on hand Green = 3 days on hand |  | Customer | Program# | # of parts supplied
|  | G | Kayser | VW | 1 | Inventory coverage until Aug 27th. They decreased requirements
|  | G | Stellantis | T1XX | 4 | Inventory coverage until Sep 02nd.
|  | G |  | EJ KM | 3 | Inventory coverage until Sept 10th. We continue having daily requirements adjustments
|  | G | Zoppas | LB | 2 | There are no requirements until January 2027
|  | G |  | GM A2XX | 1 | Inventory coverage until Sep 04th.
|  | G |  | GE PTAC | 2 | Inventory coverage until Sep 11th.
|  | G | Flexitech | "FORD-CD6 GM-BT1XX" | 8 | Inventory coverage until Sep 03th
Michele | SERVICE
Jeff Potter | Supplier Issues | G | No issues regarding raw material availability.
John W | Labor / Overtime | G | Packaging staff needed
John W. | Daily Efficiency 85%> = Green 69-84% = Yellow 69% < = Red | G | Work Center Group | % | Notes
85%
0%
95%
100%
John W | Downtime Analysis |  |  | TTL Hours | Reason Percentage | Notes
|  |  | Daily DT | 15.47
No scheduled
No scheduled
No scheduled
No scheduled
No scheduled
John W | Operations Update - Critical Issues | Y | P11 No scheduled. P21 No scheduled. P41 830/831 for NYX. P42 55237/38 for Zoppas, no critical issues. P43 2919 for TK MX no critical issues WC01 853 for stellantis no critical issues. WC02 No scheduled. PW01 853 for Stellantis no critical issues RW01 No scheduled
John W | MFG Mishit Reports | G | No Issues.
John W | Housekeeping | G | cleaned bathrooms cleaned lunch area dumped trash cleaned water from floors
John W | Change Overs | G | No Issues .
Scott | TOOLING | G | Die 225 on maintenance due to slight adjusments.
Diego | Maintenance | G | PA011 preventive maintenance, this machine will be used for Op Mobility clinching parts
Yvonne | Quality Concerns |  | ¦ ¦ External- No Concerns ¦ ¦ External- No Concerns

## Thursday 8.20.26
Email daily to: Rav Sandhu, Sherree Martin, Ron Scott, Adrian Silva, Yvonne Rodriguez, Kofi Oduro, Melissa Gardynik; Scott Jones Email report daily at 5 pm.
SLP Daily Update - Thursday 8.20.26 - Submitted to Executive Team by 5 pm
Responsible Party | Measurable | Status G/Y/R | Comments / Explanation
Nicole | EHS | G | Safety: 954 days without an incident
Nicole | Staffing Issues | G | 2nd Quarter 2026 DL Requirements: 9 There are no production operations tomorrow. SLP DL = N/A IDL = N/A Planned Absenteeism (Adv notice/approval): DL : N/A IDL: N/A Unplanned Absenteeism (call off/leave early): DL =N/A IDL =N/A
| Current Year Program EOP | G | TK MX: A2LL EOP Jul 2026 Zoppas: PTAC EOP Dec 2026
Michelle | Prem. Freight / Customer Notes | G | No issues regarding raw material availability.
Michelle | On Time Delivery | G | No Issues.
Michelle | Customer Invty Status Red = 1 day on hand Yellow = 2 days on hand Green = 3 days on hand |  | Customer | Program# | # of parts supplied
|  | G | Kayser | VW | 1 | Inventory coverage until Aug 27th. They decreased requirements
|  | G | Stellantis | T1XX | 4 | Inventory coverage until Sep 02nd.
|  | G |  | EJ KM | 3 | Inventory coverage until Sept 10th. We continue having daily requirements adjustments
|  | G | Zoppas | LB | 2 | There are no requirements until January 2027
|  | G |  | GM A2XX | 1 | Inventory coverage until Sep 04th.
|  | G |  | GE PTAC | 2 | Inventory coverage until Sep 11th.
|  | G | Flexitech | "FORD-CD6 GM-BT1XX" | 8 | Inventory coverage until Sep 03th
Michele | SERVICE
Jeff Potter | Supplier Issues | G | No issues regarding raw material availability.
John W | Labor / Overtime | G | Packaging staff needed
John W. | Daily Efficiency 85%> = Green 69-84% = Yellow 69% < = Red | G | Work Center Group | % | Notes
92%
0%
0%
100%
John W | Downtime Analysis |  |  | TTL Hours | Reason Percentage | Notes
|  |  | Daily DT | 15.47
No scheduled
No scheduled
No scheduled
No scheduled
No scheduled
John W | Operations Update - Critical Issues | Y | P11 No scheduled. P21 No scheduled. P41 No scheduled P42 55237/38 for Flexitech, no critical issues. P43 No scheduled WC01 No scheduled. WC02 No scheduled. PW01 No scheduled RW01 No scheduled
John W | MFG Mishit Reports | G | No Issues.
John W | Housekeeping | G | cleaned bathrooms cleaned lunch area dumped trash cleaned water from floors
John W | Change Overs | G | No Issues .
Scott | TOOLING | G | Die 225 on maintenance due to slight adjusments.
Diego | Maintenance | G | PA011 preventive maintenance, this machine will be used for Op Mobility clinching parts
Yvonne | Quality Concerns |  | ¦ ¦ External- No Concerns ¦ ¦ External- No Concerns