## Monday 6.22.26
Email daily to: Rav Sandhu, Sherree Martin, Ron Scott, Adrian Silva, Yvonne Rodriguez, Kofi Oduro, Melissa Gardynik; Scott Jones Email report daily at 5 pm.
GAP Daily Update - Monday 6.22.26 - Submitted to Executive Team by 5 pm
Responsible Party | Measurable | Status G/Y/R | Comments / Explanation
Nicole | EHS | G
Nicole | Staffing Issues | G | 2026 Q2 DL Requirement: 25 New Hires: Irma Hernandez. Tania Molina Staff Changes: Total GAP Employees MINUS LOA: DL: 24 IDL: 10 Total Present: DL = 22 IDL = 10 Planned Absenteeism (Adv notice/approval): DL: Kulwant Singh IDL: Unplanned Absenteeism DL: Maria Molina IDL: Other: Kulwant Singh retires in August. IDL - Alfred Strauch (medical ~ 2 months)
| Current Year Program EOP | G
Michelle | Prem. Freight / Customer Notes | G
Michelle | On Time Delivery | G
Michelle | Customer Invty Status Red = 1 day on hand Yellow = 2 days on hand Green = 3 days on hand |  | Customer | Program# | # of parts supplied
|  | G | GM-SH | C1UL | 2 | 613 -7/20, 614-7/20
|  | G | GM-FZ | BT1FG | 2 | 936-7/20, 937-7/27
|  | G |  | BT1UG | 4 | 059-9/14, 060-9/14 679-3/1/27
|  | G | GM-WTZVL | GMT610- Hinge | 4 | 237-7/8 238-7/8, 282 - 7/11, 644 - 7/13
|  | G |  | GMT610 Roller Brkt | 3 | 340-7/10, 566-7/20, 567-7/13
|  | G |  | GMT610 Check | 1 | 133-7/27
|  | G | EAP | BT1YL | 4 | 9/1
|  | G | FCA | DT | 1 | 6/24
|  | G |  | WL | 2 | No requirements
|  | G |  | WS | 2 | 510 - 6/23 511 - 6/24
|  | G | CIE-MX | WK/WL | 1 | 8/3
|  | G | CIE-AH | WS | 1 | 7/20
|  | G | Kongsburg | K-T680/T880 | 1 | 7/2
|  | G | Lear - KY | WS | 1 | 7/13
|  | G | Lear - MX | T1XX | 2 | 193-7/6 199-7/8
|  | G | Metalsa A | JL-PHEV | 3 | JL-7/2, J9-7/9
|  | G | Metalsa O | JT | 2 | 020-7/8, 027-7/8
|  | G | NYX - LIVONIA | S650 | 2 | 6/25
|  | G | Toyo | 500B | 13 | 6/22
|  | G | AGG | JL | 4 | JL-6/26-J9-6/23
Michele | SERVICE | G | GM-CCA - 13503000 Ok to ship on 7/6/26 AGG-SVC — JK Hutchinson — 2
Jeff Potter | Supplier Issues | G | No issues
John W | Labor / Overtime | Y | Direct Labor - Indirect Labor - Angelo Patterson - vacation day - Alfred Strauch - Non-work related medical RTW Open GL position - Team recruiting open positions - Hand MIG weld and GL Auto - 8 hours Die Set - 8 hours - Weld area - W513 and W514 - 10 hours - Pat M and Marcus P W507 Hand MIG. Weld - 10 hours - W513 and W514 - Tower Bank CNC - 8 hours Pack area - 10 hours - PK02 - PK03 - PK04 - Tower Bank Assembly - 8 hours Line Die - 8 hours -
John W. | Daily Efficiency 85%> = Green 69-84% = Yellow 69% < = Red |  | Work Center Group | % | Notes
90%
99%
100%
98%
John W | Downtime Analysis |  |  | TTL Hours | Reason Percentage | Notes
|  |  | Daily DT | 15.47
W514 Burn through X2 - Shut off fault X7 - Robot fault 1 - P109 die lube pump
P115 - feeder adjustments
610E C/O - 610 G - A837 - W515 C/O
John W | Operations Update - Critical Issues | G | Auto area - P100 Dispatch clear - Reviewing customer requirements P102 Dispatch cleared - Reviewing P106 C2750 - Going in next P108 C2214 - FPA obtained - 07/07 run date P109 C5812 - Running P112 C2226/76 FPA obtained - 07/06 run date P114 C47054/6472 - 13.5K run completed - Dispatch cleared - Reviewing P115 C9287 - Running P116 C32626 - Running Line Die - No major concerns PS202 - 3388-30 - Run completed PS205 - GM610 - 84509133 - Not scheduled PS209 - Z05152-7 - Not scheduled PS218 - 5126-6-10/20- Not scheduled PS219 - 5128-7-10/20 - Not scheduled Weld area - Welder 514 - Repair completed - Running both fixtures - Need to schedule further repairs when inventory levels allow (AGG bank build) - Team need approximately 9 hours to complete CNC - 5816-20 - Running W05- 5128-7-10 - Run completed - C/O to 5103-10 - Run completed - C/O to 5103-20 W507 - 5104/05 - Run completed W513 - 2118-10 - Run completed - C/O to 1873-10 - Running W514 - 69573-10- Burn through and Fault issue - Running W515 - 3388-10 - Running W516 - 5816-10 - Running Assembly - A886 - 23186613 - Run scheduled for 07/01 - 23186614 - Run scheduled for 07/01 A500 - C20001011A - Not scheduled A838 - 22934282 - Run completed - A839 - 84141644 - Running - A837- 15150237 - Running 610 E , F , G - 610F - 20814566- Run completed- 610G 15837340- Running- 610E 20814567- run completed A891 - run completed A892 - 6059-10 - Scheduled to run 06/24 - 6060-10 - scheduled to run 06/25 A893 - A894 - A889 - A890 - Scheduled to run 06/25 MAN - 4615-3 - Not scheduled
John W | MFG Mishit Reports | G | None
John W | Housekeeping | Y | Floor scrubber needed to maintain clean floors - Team looking into repair cost for EAP's old scrubber - No timing communicated out - Quote for replacement parts submitted 06/22 Housekeeping projects - None EOS Daily housekeeping - Completed
John W | Change Overs | G | P108 P112
Scott | TOOLING | G | C9224 is in for a full pm. Cleaned die. Stripped die down. Working on cams. Raised lower form button .030. Working with Leroy to make a spare upper post and lower notch punches. Sharpening where needed. Ordered tru strip springs to replace broken ones. Should be here tomorrow than will reassemble C2264 pm is complete C199AA-11 was brought in for a pm. Cleaned die. Starting on pm Sand blaster was brought in to work on per John to rework parts. Scott Scheduled 9 hours Unscheduled 0 hours Nick Scheduled 8 hours Unscheduled 0 hours
Diego | Maintenance | G | Pm's completed on waste water, drums, air compressors & air dryers. Change over on W05 make new pins for fixtures on welder 514.
Yvonne | Quality Concerns |  | ¦ ¦ No new issues

## Tuesday 6.23.26
Email daily to: Rav Sandhu, Sherree Martin, Ron Scott, Adrian Silva, Yvonne Rodriguez, Kofi Oduro, Melissa Gardynik; Scott Jones Email report daily at 5 pm.
GAP Daily Update - Tuesday 6.23.26 - Submitted to Executive Team by 5 pm
Responsible Party | Measurable | Status G/Y/R | Comments / Explanation
Nicole | EHS | G
Nicole | Staffing Issues | G | 2026 Q2 DL Requirement: 25 New Hires: Staff Changes: Term Maria Molina Total GAP Employees MINUS LOA: DL: 23 IDL: 10 Total Present: DL = 23 IDL = 10 Planned Absenteeism (Adv notice/approval): DL: IDL: Unplanned Absenteeism DL: IDL: Other: Kulwant Singh retires in August. IDL - Alfred Strauch (medical ~ 2 months)
| Current Year Program EOP | G
Michelle | Prem. Freight / Customer Notes | G
Michelle | On Time Delivery | G
Michelle | Customer Invty Status Red = 1 day on hand Yellow = 2 days on hand Green = 3 days on hand |  | Customer | Program# | # of parts supplied
|  | G | GM-SH | C1UL | 2 | 613 -7/20, 614-7/20
|  | G | GM-FZ | BT1FG | 2 | 936-7/20, 937-7/27
|  | G |  | BT1UG | 4 | 059-9/14, 060-9/14 679-3/1/27
|  | G | GM-WTZVL | GMT610- Hinge | 4 | 237-7/8 238-7/8, 282 - 7/11, 644 - 7/13
|  | G |  | GMT610 Roller Brkt | 3 | 340-7/10, 566-7/20, 567-7/13
|  | G |  | GMT610 Check | 1 | 133-7/27
|  | G | EAP | BT1YL | 4 | 9/1
|  | G | FCA | DT | 1 | 6/29
|  | G |  | WL | 2 | No requirements
|  | G |  | WS | 2 | 510 - 6/25 511 - 6/29
|  | G | CIE-MX | WK/WL | 1 | 8/3
|  | G | CIE-AH | WS | 1 | 7/20
|  | G | Kongsburg | K-T680/T880 | 1 | 7/2
|  | G | Lear - KY | WS | 1 | 7/13
|  | G | Lear - MX | T1XX | 2 | 193-7/8 199-8/16
|  | G | Metalsa A | JL-PHEV | 3 | JL-6/25, J9-7/2
|  | G | Metalsa O | JT | 2 | 020-7/8, 027-7/8
|  | G | NYX - LIVONIA | S650 | 2 | 7/9
|  | G | Toyo | 500B | 13 | 6/22
|  | G | AGG | JL | 4 | JL-6/26-J9-6/23
Michele | SERVICE | G | GM-CCA - 13503000 Ok to ship on 7/6/26 AGG-SVC — JK Hutchinson — 2
Jeff Potter | Supplier Issues | G | No issues
John W | Labor / Overtime | Y | Direct Labor - Maria Molina - absent - Terminated 06/23 Indirect Labor - Alfred Strauch - Non-work related medical RTW Open GL position - Team recruiting open positions - Hand MIG weld and GL Auto - 8 hours Die Set - 8 hours - Weld area - W513 and W514 - 10 hours - Pat M and Marcus P W507 Hand MIG - 8 hours CNC - 8 hours Pack area - 10 hours - PK02 - PK03 - PK04 - Tower Bank Assembly - 8 hours Line Die - 8 hours -
John W. | Daily Efficiency 85%> = Green 69-84% = Yellow 69% < = Red |  | Work Center Group | % | Notes
95%
99%
100%
99%
John W | Downtime Analysis |  |  | TTL Hours | Reason Percentage | Notes
|  |  | Daily DT | 15.47
W514 Shut off / start fault X4 P109 scrap shaker
P106 - P108 -P109 - P114
610E C/O - 610 G - A837 - W515 C/O
John W | Operations Update - Critical Issues | Y | Auto area - P100 Dispatch clear - Reviewing customer requirements P102 Dispatch cleared - Reviewing P106 C2750 - Die set - In FPA P108 C2214 - Ready to run - 07/07 run date P109 C5812 - 7K run completed P112 C2226/76 FPA obtained - 07/06 run date P114 C47054/6472 - Die pulled for Tooling PM - Dispatch cleared - Reviewing P115 C9287 - Running P116 C32626 - Running Line Die - No major concerns PS202 - 3388-30 - Running PS205 - GM610 - 84509133 - Not scheduled PS209 - Z05152-7 - Not scheduled PS218 - 5126-6-10/20- Not scheduled PS219 - 5128-7-10/20 - Not scheduled Weld area - Welder 514 - Repair completed - Running both fixtures - Need to schedule further repairs when inventory levels allow (AGG bank build) - Team need approximately 9 hours to complete CNC - 5816-20 - Running W05- 5128-7-10 - Run completed - C/O to 5103-10 - Run completed - C/O to 5103-20 W507 - 5104/05 - Run completed W513 - 1873-10 - Running W514 - 69573-10- Burn through and Fault issue - Running W515 - 3388-10 - Running W516 - 5816-10 - Running Assembly - A886 - 23186613 - Run scheduled for 07/01 - 23186614 - Run scheduled for 07/01 A500 - C20001011A - Not scheduled A838 - 22934282 - Run completed - A839 - 84141644 - Running - A837- 15150237 - Running 610 E , F , G - 610F - 20814566- Run completed- 610G 15837340- Running- 610E 20814567- run completed A891 - run completed A892 - 6059-10 - Scheduled to run 06/24 - 6060-10 - scheduled to run 06/25 A893 - A894 - A889 - A890 - Scheduled to run 06/25 MAN - 4615-3 - Not scheduled
John W | MFG Mishit Reports | G | None
John W | Housekeeping | Y | Floor scrubber needed to maintain clean floors - Team looking into repair cost for EAP's old scrubber - No timing communicated out - Quote for replacement parts submitted 06/22 Housekeeping projects - None EOS Daily housekeeping - Completed
John W | Change Overs | G | P114 Pulled die cleaned bolster P109 Pulled die cleaned bolster P106 Die change P108 Finish Die change
Scott | TOOLING | G | C9224 pm is complete C199AA-11 was brought in for a pm. Cleaned die. Starting on pm. Replaced worn shoulder retainers and punches. Welded and ground low area on punch retainer riser plate. Stripping die down to enter new cutoff details to check breakage. Sharpening where needed Sand blaster is ready to rework parts. New sand was bought and works good Scott Scheduled 9 hours Unscheduled 0 hours Nick Scheduled 8 hours Unscheduled 0 hours
Diego | Maintenance | G | Pm's completed on welders, all but welder 514. not released for pm. Change over on W05, & welder 515. working on making new base fixture for W514 to test. goal is to replace all 4 fixtures with updated ones.
Yvonne | Quality Concerns |  | ¦ ¦ No new issues

## Wednesday 6.24.26
Email daily to: Rav Sandhu, Sherree Martin, Ron Scott, Adrian Silva, Yvonne Rodriguez, Kofi Oduro, Melissa Gardynik; Scott Jones Email report daily at 5 pm.
GAP Daily Update - Wednesday 6.24.26 - Submitted to Executive Team by 5 pm
Responsible Party | Measurable | Status G/Y/R | Comments / Explanation
Nicole | EHS | G
Nicole | Staffing Issues | G | 2026 Q2 DL Requirement: 25 New Hires: Staff Changes: Total GAP Employees MINUS LOA: DL: 23 IDL: 10 Total Present: DL = 23 IDL = 9 Planned Absenteeism (Adv notice/approval): DL: IDL: Unplanned Absenteeism DL: IDL: Patric Salada Other: Kulwant Singh retires in August. IDL - Alfred Strauch (medical ~ 2 months)
| Current Year Program EOP | G
Michelle | Prem. Freight / Customer Notes | G
Michelle | On Time Delivery | G
Michelle | Customer Invty Status Red = 1 day on hand Yellow = 2 days on hand Green = 3 days on hand |  | Customer | Program# | # of parts supplied
|  | G | GM-SH | C1UL | 2 | 613 -7/20, 614-7/20
|  | G | GM-FZ | BT1FG | 2 | 936-7/20, 937-7/27
|  | G |  | BT1UG | 4 | 059-9/14, 060-9/14 679-3/1/27
|  | G | GM-WTZVL | GMT610- Hinge | 4 | 237-7/8 238-7/8, 282 - 7/11, 644 - 7/13
|  | G |  | GMT610 Roller Brkt | 3 | 340-7/10, 566-7/20, 567-7/13
|  | G |  | GMT610 Check | 1 | 133-7/27
|  | G | EAP | BT1YL | 4 | 9/1
|  | G | FCA | DT | 1 | 7/9
|  | G |  | WL | 2 | No requirements
|  | G |  | WS | 2 | 510 - 7/1 511 - 6/30
|  | G | CIE-MX | WK/WL | 1 | 8/3
|  | G | CIE-AH | WS | 1 | 7/20
|  | G | Kongsburg | K-T680/T880 | 1 | 7/2
|  | G | Lear - KY | WS | 1 | 7/13
|  | G | Lear - MX | T1XX | 2 | 193-7/8 199-8/16
|  | G | Metalsa A | JL-PHEV | 3 | JL-7/2, J9-7/2
|  | G | Metalsa O | JT | 2 | 020-7/8, 027-7/8
|  | G | NYX - LIVONIA | S650 | 2 | 7/9
|  | G | Toyo | 500B | 13 | 7/6
|  | G | AGG | JL | 4 | JL-6/26-J9-6/23
Michele | SERVICE | G | GM-CCA - 13503000 Ok to ship on 7/6/26 AGG-SVC — JK Hutchinson — 2
Jeff Potter | Supplier Issues | G | No issues
John W | Labor / Overtime | Y | Direct Labor - Maria Molina - Terminated 06/23 Indirect Labor - Alfred Strauch - Non-work related medical RTW Open GL position - Team recruiting open positions - Hand MIG weld and GL Auto - 8 hours Die Set - 8 hours - Weld area - W513 and W514 - 10 hours - Pat M and Marcus P W507 Hand MIG - 8 hours CNC - 8 hours Pack area - 10 hours - PK02 - PK03 - PK04 - Tower Bank Assembly - 8 hours Line Die - 8 hours -
John W. | Daily Efficiency 85%> = Green 69-84% = Yellow 69% < = Red |  | Work Center Group | % | Notes
99%
99%
100%
99%
John W | Downtime Analysis |  |  | TTL Hours | Reason Percentage | Notes
|  |  | Daily DT | 15.47
W514 Shut off / start fault X5 - A838 Cylinder stuck
P106
610E C/O - 610 G - A837 - W515 C/O
John W | Operations Update - Critical Issues | G | Auto area - P100 Dispatch clear - Reviewing customer requirements P102 Dispatch cleared - Reviewing P106 C2750 - Running P108 C2214 - Ready to run - 07/07 run date P109 C5812 - 7K run completed - Press cleared P112 C2226/76 - Running P114 C47054/6472 - Press cleared - Reviewing P115 C9287 - Running P116 C32626 - 60K run completed - C7085 - Going in next Line Die - No major concerns PS202 - 3388-30 - Run completed PS205 - GM610 - 84509133 - Not scheduled PS209 - Z05152-7 - Not scheduled PS218 - 5126-6-10/20- Not scheduled PS219 - 5128-7-10/20 - Not scheduled Weld area - Welder 514- Need to schedule further repairs when inventory levels allow (AGG bank build) - Team needs approximately 9 hours to complete CNC - 5816-20 - Running W05- 5103-20 - Run completed - C/O to 5122-10 W507 - 5104/05 - Not scheduled W513 - 1873-10 - Run completed - C/O to 20019-10 W514 - 69573-10- Faults X5 - Running W515 - 3388-10 - Running W516 - 5816-10 - Running Assembly - A886 - 23186613 - Run scheduled for 07/01 - 23186614 - Run scheduled for 07/01 A500 - C20001011A - Not scheduled A838 - 22934282 - Run completed - A839 - 84141644 - Running - A837- 15150237 - Running 610 E , F , G - 610F - 20814566- Run completed- 610G 15837340- Running- 610E 20814567- run completed A891 - run completed A892 - 6059-10 - Scheduled to run 06/24 - 6060-10 - scheduled to run 06/25 A893 - A894 - A889 - A890 - Scheduled to run 06/25 MAN - 4615-3 - Not scheduled
John W | MFG Mishit Reports | G | None
John W | Housekeeping | Y | Floor scrubber needed to maintain clean floors - Team looking into repair cost for EAP's old scrubber - No timing communicated out - Replacement ordered - Diego to report out timing Housekeeping projects - None EOS Daily housekeeping - Completed
John W | Change Overs | G | P116 Start die change P106 Finished die change
Scott | TOOLING | G | C199AA-11 Entered new cutoff detail. Breakage was off. Reset to breakage. Finished pm. Will reassemble tomorrow C9224 pm is complete. On horses for next wednesday review C32626 will be in next for wednesday review C287 will be in after the run for wednesday review Sand blaster is ready to rework parts. New sand was bought and works good Scott Scheduled 9 hours Unscheduled 0 hours Nick Scheduled 8 hours Unscheduled 0 hours
Diego | Maintenance | G | pm's on hilo's complete. Change over on W05, & welder 515. working on making new base fixture for W514 to test. goal is to replace all 4 fixtures with updated ones. Diego to AAP (9 mile & 10 mile)
Yvonne | Quality Concerns |  | ¦ ¦ No new issues

## Thursday 6.25.26
Email daily to: Rav Sandhu, Sherree Martin, Ron Scott, Adrian Silva, Yvonne Rodriguez, Kofi Oduro, Melissa Gardynik; Scott Jones Email report daily at 5 pm.
GAP Daily Update - Thursday 6.25.26 - Submitted to Executive Team by 5 pm
Responsible Party | Measurable | Status G/Y/R | Comments / Explanation
Nicole | EHS | G
Nicole | Staffing Issues | G | 2026 Q2 DL Requirement: 25 New Hires: Staff Changes: Total GAP Employees MINUS LOA: DL: 23 IDL: 10 Total Present: DL = 22 IDL = 10 Planned Absenteeism (Adv notice/approval): DL: Diane Mitchell IDL: Unplanned Absenteeism DL: IDL: Other: Kulwant Singh retires in August. IDL - Alfred Strauch (medical ~ 2 months)
| Current Year Program EOP | G
Michelle | Prem. Freight / Customer Notes | G
Michelle | On Time Delivery | G
Michelle | Customer Invty Status Red = 1 day on hand Yellow = 2 days on hand Green = 3 days on hand |  | Customer | Program# | # of parts supplied
|  | G | GM-SH | C1UL | 2 | 613 -7/20, 614-7/20
|  | G | GM-FZ | BT1FG | 2 | 936-7/20, 937-7/27
|  | G |  | BT1UG | 4 | 059-9/14, 060-9/14 679-3/1/27
|  | G | GM-WTZVL | GMT610- Hinge | 4 | 237-7/20 238-7/2, 282 - 7/17, 644 - 7/20
|  | G |  | GMT610 Roller Brkt | 3 | 340-7/27, 566-7/20, 567-7/27
|  | G |  | GMT610 Check | 1 | 133-7/27
|  | G | EAP | BT1YL | 4 | 9/1
|  | G | FCA | DT | 1 | 7/9
|  | G |  | WL | 2 | No requirements
|  | G |  | WS | 2 | 510 - 7/13 511 - 7/10
|  | G | CIE-MX | WK/WL | 1 | 8/3
|  | G | CIE-AH | WS | 1 | 7/20
|  | G | Kongsburg | K-T680/T880 | 1 | 7/2
|  | G | Lear - KY | WS | 1 | 7/13
|  | G | Lear - MX | T1XX | 2 | 193-7/8 199-8/16
|  | G | Metalsa A | JL-PHEV | 3 | JL-7/2, J9-7/2
|  | G | Metalsa O | JT | 2 | 020-7/8, 027-7/8
|  | G | NYX - LIVONIA | S650 | 2 | 7/9
|  | G | Toyo | 500B | 13 | 7/6
|  | G | AGG | JL | 4 | JL-6/26-J9-6/23
Michele | SERVICE | G | GM-CCA - 13503000 Ok to ship on 7/6/26 AGG-SVC — JK Hutchinson — 2
Jeff Potter | Supplier Issues | G | No issues
John W | Labor / Overtime | Y | Direct Labor - Maria Molina - Terminated 06/23 Indirect Labor - Alfred Strauch - Non-work related medical RTW Open GL position - Team recruiting open positions - Hand MIG weld and GL Auto - 8 hours Die Set - 8 hours - Weld area - W513 and W514 - 10 hours - Pat M and Marcus P W507 Hand MIG - 8 hours CNC - 8 hours Pack area - 10 hours - PK02 - PK03 - Tower Bank Assembly - 8 hours Line Die - 8 hours -
John W. | Daily Efficiency 85%> = Green 69-84% = Yellow 69% < = Red |  | Work Center Group | % | Notes
96%
92%
100%
97%
John W | Downtime Analysis |  |  | TTL Hours | Reason Percentage | Notes
|  |  | Daily DT | 15.47
A886 1.21 Robot issue W514 .23 A839 .29
193AA Adjusted for failed feeler check
P115 -P112
W515 C/O -
John W | Operations Update - Critical Issues | G | Auto area - P100 Dispatch clear - Reviewing customer requirements P102 Dispatch cleared - Reviewing P106 C2750 - Running P108 C2214 - Ready to run - 07/07 run date P109 C5812 - 7K run completed - Press cleared P112 C2226/76 - 10K run completed - C3115/65 - FPA obtained - Ready to run P114 Press cleared - Reviewing P115 C9287 - 126K run completed - C193AA - FPA obtained - Ready to run P116 C32626 - 60K run completed - C7085 - FPA obtained - Ready to run Line Die - No major concerns PS202 - 3388-30 - Not scheduled PS205 - GM610 - 84509133 - Not scheduled PS209 - Z05152-7 - Not scheduled PS218 - 5126-6-10/20- Not scheduled PS219 - 5128-7-10/20 - Not scheduled Weld area - Welder 514- Need to schedule further repairs when inventory levels allow (AGG bank build) - Team needs approximately 9 hours to complete CNC - 5816-20 - Running W05- 5122-10 - run completed - C/O to 5122-20 run completed - C/O to 5126-6 - Running W507 - 5104/05 - Not scheduled W513 - 20019-10 - Run completed - C/O to 69573-10 - Running W514 - 69573-10- Faults X5 - Running W515 - 3388-10 - Run completed - C/O to 3388-20 - Running W516 - 5816-10 - Running Assembly - A886 - 23186613 - Run scheduled for 07/01 - 23186614 - Run scheduled for 07/01 A500 - C20001011A - Not scheduled A838 - 22934282 - Run completed - A839 - 84141644 - Running - A837- 15150237 - Running 610 E , F , G - 610F - 20814566- Run completed- 610G 15837340- Running- 610E 20814567- run completed A891 - run completed A892 - 6059-10 - Scheduled to run 06/29 - 6060-10 - scheduled to run 06/29 A893 - A894 - A889 - A890 - Scheduled to run 06/29 MAN - 4615-3 - Not scheduled
John W | MFG Mishit Reports | G | None
John W | Housekeeping | Y | Floor scrubber needed to maintain clean floors - Team looking into repair cost for EAP's old scrubber - No timing communicated out - Replacement ordered - Diego to report out timing Housekeeping projects - None EOS Daily housekeeping - Completed
John W | Change Overs | G | P116 Finished die change P112 Die change P115 Die change
Scott | TOOLING | G | C199AA-11 pm is complete C9224 pm is complete. On horses for next wednesday review C32626 is in for a pm. After done will leave on horses for wednesday review C287 will be in next for pm and wednesday review Sand blaster is ready to rework parts. New sand was bought and works good Scott Scheduled 9 hours Unscheduled 0 hours Nick Scheduled 8 hours Unscheduled 0 hours
Diego | Maintenance | G | pm's on automation cells & line die presses complete. Change over on W05, & welder 515 & Welder 513 working on making new base fixture for W514 to test. goal is to replace all 4 fixtures with updated ones.
Yvonne | Quality Concerns |  | ¦ ¦ No new issues

## Friday 6.26.26
Email daily to: Rav Sandhu, Sherree Martin, Ron Scott, Adrian Silva, Yvonne Rodriguez, Kofi Oduro, Melissa Gardynik; Scott Jones Email report daily at 5 pm.
GAP Daily Update - Friday 6.26.26 - Submitted to Executive Team by 5 pm
Responsible Party | Measurable | Status G/Y/R | Comments / Explanation
Nicole | EHS | G
Nicole | Staffing Issues | G | 2026 Q2 DL Requirement: 25 New Hires: Staff Changes: Total GAP Employees MINUS LOA: DL: 23 IDL: 10 Total Present: DL = 21 IDL = 8 Planned Absenteeism (Adv notice/approval): DL: Diane Mitchell IDL: Chrissi Adams Unplanned Absenteeism DL: Omar Galvan IDL: Leory Mikolowski Other: Kulwant Singh retires in August. IDL - Alfred Strauch (medical ~ 2 months)
| Current Year Program EOP | G
Michelle | Prem. Freight / Customer Notes | G
Michelle | On Time Delivery | G
Michelle | Customer Invty Status Red = 1 day on hand Yellow = 2 days on hand Green = 3 days on hand |  | Customer | Program# | # of parts supplied
|  | G | GM-SH | C1UL | 2 | 613 -7/20, 614-7/20
|  | G | GM-FZ | BT1FG | 2 | 936-7/20, 937-7/27
|  | G |  | BT1UG | 4 | 059-9/14, 060-9/14 679-3/1/27
|  | G | GM-WTZVL | GMT610- Hinge | 4 | 237-7/20 238-7/2, 282 - 7/17, 644 - 7/20
|  | G |  | GMT610 Roller Brkt | 3 | 340-7/27, 566-7/20, 567-7/27
|  | G |  | GMT610 Check | 1 | 133-7/27
|  | G | EAP | BT1YL | 4 | 9/1
|  | G | FCA | DT | 1 | 7/9
|  | G |  | WL | 2 | No requirements
|  | G |  | WS | 2 | 510 - 7/14 511 - 7/13
|  | G | CIE-MX | WK/WL | 1 | 8/3
|  | G | CIE-AH | WS | 1 | 7/20
|  | G | Kongsburg | K-T680/T880 | 1 | 7/2
|  | G | Lear - KY | WS | 1 | 7/13
|  | G | Lear - MX | T1XX | 2 | 193-7/8 199-8/16
|  | G | Metalsa A | JL-PHEV | 3 | JL-7/30, J9-7/9
|  | G | Metalsa O | JT | 2 | 020-7/8, 027-7/8
|  | G | NYX - LIVONIA | S650 | 2 | 7/16
|  | G | Toyo | 500B | 13 | 7/6
|  | G | AGG | JL | 4 | JL-7/2-J9-7/17
Michele | SERVICE | G | GM-CCA - 13503000 Ok to ship on 7/6/26 AGG-SVC — JK Hutchinson — 2
Jeff Potter | Supplier Issues | G | No issues
John W | Labor / Overtime | Y | Direct Labor - Maria Molina - Terminated 06/23 - Omar G called off - Family emergency Indirect Labor - Alfred Strauch - Non-work related medical RTW Open GL position - Team recruiting open positions - Hand MIG weld and GL Auto - 8 hours Die Set - 8 hours - Weld area - W513 and W514 - 10 hours - Pat M and Marcus P W507 Hand MIG - 8 hours CNC - 8 hours Pack area - hours - Assembly - 8 hours Line Die - 8 hours -
John W. | Daily Efficiency 85%> = Green 69-84% = Yellow 69% < = Red |  | Work Center Group | % | Notes
94%
99%
98%
99%
John W | Downtime Analysis |  |  | TTL Hours | Reason Percentage | Notes
|  |  | Daily DT | 15.47
PA106 Die lube pump -W515 poor weld condition
193AA Adjusted for failed feeler check
P115 - 193AA
W05 - A893 - W515 C/O 1.28
John W | Operations Update - Critical Issues | G | Auto area - P100 Dispatch clear - Reviewing customer requirements P102 Dispatch cleared - Reviewing P106 C2750 - 7K run completed - C47054/64722 - Going in next P108 C2214 - Ready to run - 07/07 run date P109 C5812 - 7K run completed - Press cleared P112 C3115/65 - 8K of 15K run completed - Remainder of steel due in week of 06/29 P114 C44897/64738 - Going in next P115 C9287 - 126K run completed - C193AA - FPA obtained - Ready to run P116 C7085 - Running Line Die - No major concerns PS202 - 3388-30 - Run completed - 1,224 ready for OSP PS205 - GM610 - 84509133 - Running PS209 - Z05152-7 - Not scheduled PS218 - 5126-6-10/20- Not scheduled PS219 - 5128-7-10/20 - Not scheduled Weld area - Welder 514- Need to schedule further repairs when inventory levels allow (AGG bank build) - Team needs approximately 9 hours to complete CNC - 5816-20 - Running W05- 5122-20 - Running W507 - 5104/05 - Not scheduled W513 - 69573-10 - Running W514 - 69573-10- Running W515 - 3388-20 - 1224 piece run completed - C/O to 3388-10 - Running W516 - 5816-10 - Running Assembly - A886 - 23186613 - Run scheduled for 07/01 - 23186614 - Run scheduled for 07/01 A500 - C20001011A - Not scheduled A838 - 22934282 - Run completed - A839 - 84141644 - Running - A837- 15150237 - Running 610 E , F , G - 610F - 20814566- Run completed- 610G 15837340- Running- 610E 20814567- run completed A891 - run completed A892 - 6059-10 - Scheduled to run 06/29 - 6060-10 - scheduled to run 06/29 A893 - A894 - A889 - A890 - Running MAN - 4615-3 - Not scheduled
John W | MFG Mishit Reports | G | None
John W | Housekeeping | Y | Floor scrubber needed to maintain clean floors - Team looking into repair cost for EAP's old scrubber - No timing communicated out - Replacement ordered - Diego to report out timing Housekeeping projects - None EOS Daily housekeeping - Completed
John W | Change Overs | G | P106 In die change P114 In die change
Scott | TOOLING | G | C9224 pm is complete. On horses for next wednesday review C32626 is in for a pm. After done will leave on horses for wednesday review C287 is in for a pm and than will have ready for wednesday review. Sand blaster is ready to rework parts. New sand was bought and works good Scott Scheduled 9 hours Unscheduled 0 hours Nick Scheduled 8 hours Unscheduled 0 hours
Diego | Maintenance | G | pm's on auto presses complete. . Change over on W05, & welder 515 working on making new base fixture for W514 to test. goal is to replace all 4 fixtures with updated ones.
Yvonne | Quality Concerns |  | ¦ ¦ No new issues